## CENTRA BUGS
SNO | DATE | NAME | HQOW/ ROW | SB | SR | STATUS | DA STATUS | IS SOURCE STOP | TESTED BY | Ticket ID | REMARKS
1 | 2025-01-02 | ORDER TRANSACTIONS REPORT – THIS REPORT SHOW ALL THE REGION TRANSACTION'S. BUT IT SHOULD SHOW LOGIN REGION TRANSACTION'S DETAILS ONLY. | ROW | SALES MANAGEMENT | ORDER TRANSACTIONS REPORT | ISSUE | NYT | YES | MANJULA
2 | 2025-01-02 | BELOW MENTIONED REPORT'S MISSING IN CENTRA. - MASTER VENDOR CHANGE LIST - BUSINESS PARTNER DETAIL - UNPACK PACKAGE REPORT | ROW | MASTER MANAGEMENT | MASTER VENDOR CHANGE LIST | ISSUE | NYT | YES | MANJULA / PRAVEEN
3 | 2025-01-02 | BELOW MENTIONED REPORT'S TAKEN LONG TIME FOR DATA LOADING. - INVOICE DETAIL & MARGIN - SELL_OUT-QUANTITY REPORT - DELIVERY CONFIRMATION DETAIL REPORT - SHIPMENT DETAILS | ROW | SALES MANAGEMENT | SELL_OUT-QUANTITY REPORT | ISSUE | NYT | YES | MANJULA / PRAVEEN
4 | 2025-01-02 | SYSTEM COULD NOT ALLOW TO CREATE NEW CONSIGNMENT ORDER GIFT(CREATE NEW ICON DISABLE) | ROW | INVENTORY MANAGEMENT | CONSIGNMENT GIFT | ISSUE | NYT | YES | MANJULA
5 | 2025-01-02 | Could not able to Import Business partner in ROW SQL Error is showing | ROW | MASTER MANAGEMENT | IMPORT DMS BUSINESS PARTNER | ISSUE | NYT | YES | SURYA | 401042
6 | 2025-01-02 | COULD NOT IMPORT THE ORDER (SHOWING ERROR IN IMPORT PROMOTION ORDER SCREEN & 7 ORG DATA) | ROW | SALES MANAGEMENT | IMPORT DMS ORDER | ISSUE | NYT | YES | SURYA / MANIRATHNAM | 401043
7 | 2025-01-02 | PROCESS BUTTON NOT MAPPED TO USER | ROW | SALES MANAGEMENT | IMPORT CUSTOMER RMA IMPORT CONSIGNMENT ORDER IMPORT CREDIT LIMIT REQUEST | ISSUE | NYT | YES | VINESH
8 | 2025-01-02 | POSTING BUTTON DISPLAYS IN ROW | ROW | INVENTORY MANAGEMENT | PHYSICAL INVENTORY | ISSUE | NYT | YES | VINESH
9 | 2025-01-02 | CONSIGNMENT ORDER - CREATE INVENTORY MOVE (LOCATOR AND LOCATOR TO) SHOWING ALL BRANCH LOCATORS IN REGION. | ROW | INVENTORY MANAGEMENT | CONSIGNMENT ORDER | ISSUE | NYT | YES | KK
10 | 2025-01-03 | CONFIRM DMS EXPORT FORM NOT SHOWING IN CENTRA ROW. | ROW | INVENTORY MANAGEMENT | CONFIRM DMS EXPORT | ISSUE | NYT | YES | HARIHARAN
11 | 2025-01-03 | CREATE BUTTON NOT WORKING | ROW | PURCHASE MANAGEMENT / INVENTORY MANAGEMENT | INVOICE(VENDOR) CONSIGNMENT GIFT METRO TRANSFER STOCKTAKE ADJUSTMENT | ISSUE | NYT | YES | SANTHOSH | 401015
12 | 2025-01-03 | TELE NO COLUMN IN PURCHASE ORDER PRINT FORMATE PO_DENEAST_VERSION_2 IS NOT PRESENT IN ROW BUT PRESENT IN CENTRA. | ROW | PURCHASE MANAGEMENT | PURCHASE ORDER | ISSUE | NYT |  | SANTHOSH | 401047
13 | 2025-01-06 | C_ORDER_HEADER_V2 PRINT FORMATE IS SHOWING IN 8182 BUT NOT SHOWING IN CENTRA HQ | HQOW | PURCHASE MANAGEMENT | PURCHASE ORDER | ISSUE | NYT |  | SANTHOSH | 401048
14 | 2025-01-06 | PRINT FORMATE ORDER_HEADER ** 1000002 **_VERSION1 IN PURCHASE ORDER PAYMENT TERM IS MISSING “ND” AND TEXT IS OVERLAPPED | HQOW | PURCHASE MANAGEMENT | PURCHASE ORDER | ISSUE | NYT |  | SANTHOSH | 401049 | CLARIFICATION
15 | 2025-01-06 | MARKETING CAMPAIGN (TRADE) SHOULD NOT LOAD IN NTA PURCHASE ORDER LINE | HQOW | PURCHASE MANAGEMENT | NTA PURCHASE ORDER | ISSUE | NYT |  | SANTHOSH | 401050
16 | 2025-01-06 | AFTER COMPLETING GOODS RECEIPT DATE ORDERED FIELD SHOULD BE EDITABLE BUT IT’S NOT IN CENTRA | HQOW | PURCHASE MANAGEMENT | GOODS RECEIPT | ISSUE | NYT |  | SANTHOSH | 401052
17 | 2025-01-06 | MENTIONED INVOICE AND DO DETAILS DID NOT SHOW IN DELIVERY CONFIRMATION DETAIL REPORT 1DO2412-12601 1AR12412-12801 | HQOW/ROW | SALES MANAGEMENT | DELIVERY CONFIRMATION DETAIL REPORT | ISSUE | NYT |  | MANJULA
18 | 2025-01-06 | LOGIN REGION TRANSACTION ONLY SHOULD SHOW IN TOTAL SALES (MTS) BY CUSTOMER. BUT CURRENCY REPORT SHOW ALL REGION DATA. EG : 434000027 (REGION 4) R4 BP SALES DETAIL SHOWING IN R1 | HQOW/ROW | SALES MANAGEMENT | TOTAL SALES (MTS) BY CUSTOMER. | ISSUE | NYT |  | MANJULA
19 | 2025-01-06 | SHIPMENT DETAIL REPORT SHOWING BOTH HQ AND ROW. THIS REPORT SHOW MANAGE DO AND CUSTOMER RETURN TRANSACTION DETAILS. TRANSACTION DETAILS SHOWING ONLY IN ROW. NO RECORD FOUND IN HQ. 1DO2412-12601 | HQOW/ROW | SALES MANAGEMENT | SHIPMENT DETAIL | ISSUE | NYT |  | MANJULA
20 | 2025-01-06 | NTA PO AND GR TRANASACTION DETAILS SHOULD NOT SHOW IN ROW. REPORT NAME : ORDER TRANSACTIONS | ROW | SALES MANAGEMENT | ORDER TRANSACTIONS | ISSUE | NYT |  | MANJULA
21 | 2025-01-06 | BP NAME AND BRANCH CHANGED MANUALLY BUT RECORD NOT SHOWING BP: 100985896 | ROW | MASTER MANAGEMENT | MASTER CUSTOMER CHANGE LIST_DIRECT | ISSUE | NYT |  | PRAVEEN
22 | 2025-01-06 | REPORTS SHOWING ONLY IN AWS - 8181 BUT NOT IN AWS - CENTRA REPORT NAME: MASTER CUSTOMER LIST_ALL | ROW | MASTER MANAGEMENT | MASTER CUSTOMER LIST_ALL | ISSUE | NYT |  | PRAVEEN
23 | 2025-01-06 | MARKETING CAMPAIGN (TRADE) SHOULD NOT LOAD IN NTA AP INVOICE LINE | HQOW | PURCHASE MANAGEMENT | NTA AP INVOICE | ISSUE | NYT |  | SANTHOSH | 401055
24 | 2025-01-06 | IMPORTED NTA PURCHASE ORDER DATE FIELD SHOWS READ ONLY | HQOW | PURCHASE MANAGEMENT | IMPORT NTA PURCHASE ORDER | ISSUE | NYT |  | HARIHARAN
25 | 2025-01-06 | IMPORTED RS – TRANSFER SHOWING BRANCH IN * IT WILL NOT MOVE TO MAIN SCREENS | ROW | INVENTORY MANAGEMENT | IIMPORT RS – TRANSFER | ISSUE | NYT |  | MANIRATHNAM
26 | 2025-01-06 | AR INVOICE REVERSAL (E_INVOICE) NOT WORKING E_INVOICES STATUS COLUMN VALUE SHOW READY TO REVERSE | ROW | SALES MANAGEMENT | MANAGE INVOICE | ISSUE | NYT |  | MANIRATHNAM
27 | 2025-01-06 | WHILE COMPLETING THE RBT THROW THE ERROR TALLY SHEET ASI IS NOT AVAILABLE | ROW | INVENTORY MANAGEMENT | RECEIVING BRANCH TRANSFER | ISSUE | NYT |  | KK
28 | 2025-01-07 | ABORT WORKFLOW PROCESS NOT SHOWING SCREEN IN ROW BUGS BUGS | ROW | MASTER MANAGEMENT | ABORT WORKFLOW PROCESS | ISSUE | NYT |  | GOBI | 401058
29 | 2025-01-07 | ATTRIBUTE INSTANCES NOT CREATE LINE IN CENTRA ROW BUGS BUGS | ROW | MASTER MANAGEMENT | ATTRIBUTE INSTANCES | ISSUE | NYT |  | GOBI | 401059
30 | 2025-01-07 | BUSINESS PAARTNER CUSTOMERLINEISSUE IN (FREIGHT) MISSING CENTRA REGION BUGS | ROW | MASTER MANAGEMENT | BUSINESS PARTNER | ISSUE | NYT |  | GOBI | 401021
31 | 2025-01-07 | CURRENCY CENTRA CUSTOM 2 SCREEN NOT SHOW.BUGS | ROW/HQOW | MASTER MANAGEMENT | CURRENCY | ISSUE | NYT |  | GOBI
32 | 2025-01-07 | DOCUMENT SQUENCE ROW (DOCUMENT TYPE) MISSING IN MAIN SCREEN.BUGS | ROW/HQOW | MASTER MANAGEMENT | DOCUMENT TYPE | ISSUE | NYT |  | GOBI
33 | 2025-01-07 | ROW CENTRA MISSING (GLCATEGORY) | ROW | MASTER MANAGEMENT | GL CATEGORY SCREEN MISSING | ISSUE | NYT |  | GOBI
34 | 2025-01-07 | GROUP OF ATTRIBUTES IN ROW CENTRA BUGS | ROW | MASTER MANAGEMENT | GROUP OF ATTRIBUTES | ISSUE | NYT |  | GOBI
35 | 2025-01-07 | IMPORT FEE GROUP MISSING IN HQOW CENTRA | HQOW | MASTER MANAGEMENT | IMPORT FEE GROUP MISSING SCREEN | ISSUE | NYT |  | GOBI
36 | 2025-01-07 | IMPORT REPORT LINE SET IS N0T SHOWING IN ROW CENTRA AWS | ROW | PURCHASE MANAGEMENT | IMPORT REPORT LINE SET | ISSUE | NYT |  | SURYA | 401064
37 | 2025-01-07 | IMPORT RS-PURCHASE IS NOTSHOWING IN ROW CENTRA AWS | ROW | PURCHASE MANAGEMENT | IMPORT RS-PURCHASE | ISSUE | NYT |  | SURYA | 401026
38 | 2025-01-07 | NTA PURCHASE ORDER AND GOODS RECEIPT REPORTS ARE VISIBLE IN CENTRA - REGION R1, BUT THEY ONLY APPEAR IN CENTRA - HEADQUARTERS, NOT IN THE REGION, REPORTS I MENTIONED BELOW: 1)PURCHASE ORDER DETAIL 2)PURCHASE ORDER SUMMARY | HQOW / ROW | PURCHASE MANAGEMENT | PURCHASE ORDER DETAIL PURCHASE ORDER SUMMARY | ISSUE | NYT |  | PRAVEEN
39 | 2025-01-07 | THIS SERVICE REQUEST VISIBLE IN CENTRA - HQ, BUT IT MISSING IN THE CENTRA - REGION R1. | HQOW / ROW | PURCHASE MANAGEMENT | PO MATCHING DETAILS | ISSUE | NYT |  | PRAVEEN
40 | 2025-01-07 | BRANCH (*) PARAMETER NOT WORKING IN AGING REPORT IN HQ. | HQOW+ROW | SALES MANAGEMENT | AGING REPORT | ISSUE | NYT |  | MANJULA
41 | 2025-01-07 | REPORT NAME : REVERSED VOID INVOICE LIST ISSUE : DATE PARAMETER NOT WORKING | HQOW+ROW | SALES MANAGEMENT | REVERSED VOID INVOICE LIST | ISSUE | NYT |  | MANJULA
42 | 2025-01-07 | REPORT NAME : SALES BY INVOICE DATE ISSUE : LOGIN REGION TRANSACTION ONLY SHOULD SHOW. BUT CURRENCY REPORT SHOW ALL REGION DATA. EG: 4AR12412-10901 REGION 4 INVOICE SHOWING IN R1 | HQOW+ROW | SALES MANAGEMENT | SALES BY INVOICE DATE | ISSUE | NYT |  | MANJULA
43 | 2025-01-07 | EARLY PAYMENT REPORT MISSING IN ROW. | HQOW+ROW | SALES MANAGEMENT | EARLY PAYMENT REPORT | ISSUE | NYT |  | MANJULA
44 | 2025-01-07 | INDIVIDUAL CREDIT REPORT SHOW DUPLICATE RECORDS. | HQOW+ROW | SALES MANAGEMENT | INDIVIDUAL CREDIT REPORT | ISSUE | NYT |  | MANJULA
45 | 2025-01-07 | REPORT NAME : SALES ORDER SUMMARY ISSUE : LOGIN REGION TRANSACTION ONLY SHOULD SHOW. BUT CURRENCY REPORT SHOW ALL REGION DATA. | HQOW+ROW | SALES MANAGEMENT | SALES ORDER SUMMARY | ISSUE | NYT |  | MANJULA
46 | 2025-01-08 | PROCESS BUTTON NOT MAPPED TO USER | ROW | SALES MANAGEMENT | IMPORT TALLY SHEET | ISSUE | NYT |  | VINESH
47 | 2025-01-09 | BRANCH SHOULD NOT BE (*) AS DEFAULT | HQOW | SALES MANAGEMENT | IMPORT CAMPAIGN MAPPING | ISSUE | NYT |  | VINESH
48 | 2025-01-08 | DEPARTMENT FIELD IS NOT SHOWING IN AWS HQ | HQOW | PURCHASE MANAGEMENT | NTA PAYMENT – AP | ISSUE | NYT |  | SANTHOSH | 401069
49 | 2025-01-08 | “BRANCH” PARAMETER SHOWING ALL REGIONS NAME IN “OUT STANDING COMMERCIAL DISCOUNT REPORT-ROW’. LOGIN REGION NAME ONLY SHOULD SHOW IN ROW. | ROW | SALES MANAGEMENT | OUT STANDING COMMERCIAL DISCOUNT REPORT-ROW | ISSUE | NYT |  | MANJULA
50 | 2025-01-08 | 1.”TRANSACTION DATE” AND “USER” PARAMETER’S MISSING IN PAYMENT TRANSACTION LOG(ROW). 2.CENTRA R1ROW AND R1ROW-8181 PRINT FORMAT NOT MATCHED. REPORT NAME : PAYMENT TRANSACTION LOG | ROW | SALES MANAGEMENT | PAYMENT TRANSACTION LOG | ISSUE | NYT |  | MANJULA
51 | 2025-01-08 | SUMMARY OUTSTANDING COMMERCIAL REPORT MISSING IN ROW. | ROW | SALES MANAGEMENT | SUMMARY OUTSTANDING COMMERCIAL REPORT | ISSUE | NYT |  | MANJULA
52 | 2025-01-08 | LOGIN REGION TRANSACTION ONLY SHOULD SHOW. BUT CURRENCY REPORT SHOW ALL REGION DATA. REPORT NAME : TOTAL SALES MTS BY SALESMAN | HQOW/ ROW | SALES MANAGEMENT | TOTAL SALES MTS BY SALESMAN | ISSUE | NYT |  | MANJULA
53 | 2025-01-08 | PRINT FORMAT EMPTY IN CUSTOMER NO SALES REPORT – ROW. SO REPORT COULD NOT ABLE TO EXPORT. | ROW | SALES MANAGEMENT | CUSTOMER NO SALES REPORT – ROW | ISSUE | NYT |  | MANJULA
54 | 2025-01-08 | 1. “BRANCH” PARAMETER SHOWING ALL REGIONS NAME IN OPEN MOVE CONFIRMATION-ROW . LOGIN REGION NAME ONLY SHOULD SHOW IN ROW. 2. OPEN MOVE CONFIRMATION REPORT SHOULD SHOW ALL REGION VALUE’S IN HQ. ALL BRANCH (*) VALUE MISSING IN BRANCH PARAMETER. | ROW | SALES MANAGEMENT | OPEN MOVE CONFIRMATION | ISSUE | NYT |  | MANJULA
55 | 2025-01-08 | MANAGE PARTNER SCREEN CENTRA UPICODE COLUMN UNNESSCCASARY BUGS | ROW | MASTER MANAGEMENT | MANAGE PARTNER | ISSUE | NYT |  | GOBI
56 | 2025-01-08 | MANAGE PARTNER UM_DeliveryRegDate UN NESSCARY SCREEN IN CENTRA ROW BUGS | HQOW | MASTER MANAGEMENT | MANAGE PARTNER | ISSUE | NYT |  | GOBI
57 | 2025-01-08 | NTA PRODUCT CATEGORY ACCOUNTING SCHEMA LINE MISSING IN CENTRA BUGS | HQOW | MASTER MANAGEMENT | NTAPRODUCT CATEGORY | ISSUE | NYT |  | GOBI
58 | 2025-01-08 | PRODUCT BRAND ISSUE IN ROW CENTRA (BRAND) ADDED BUGS | ROW | MASTER MANAGEMENT | PRODUCT BRAND | ISSUE | NYT |  | GOBI
59 | 2025-01-08 | RETURN TO POLICY ISSUE 8181 ROW CHECK CENTRA ROW RETURN TO POLICY EDITABLE BUGS | ROW | MASTER MANAGEMENT | RETURN TO POLICY | ISSUE | NYT |  | GOBI
60 | 2025-01-08 | RMA CATEGORY HQOW DOC TYPE ISSUE IN CENTRA BUGS | HQOW | MASTER MANAGEMENT | RMA CATEGORY | ISSUE | NYT |  | GOBI
61 | 2025-01-08 | THIS SERVICE REQUEST VISIBLE IN CENTRA - HQ, BUT IT MISSING IN THE CENTRA - REGION R1. BUT IT SHOWING IN THE AWS – 8181. THE FOLLOWING REPORTS ARE MENTIONED BELOW: 1) MATERIAL RECEIPT DETAILS 2) VIEW ALLOCATION REPORT AP 3) VIEW ALLOCATION REPORT AR AND ALSO PERFORMANCE ISSUES IN PDF FORMAT IT TAKES MORE TIME. | HQOW / ROW | PURCHASE MANAGEMENT & SALES MANAGEMENT | MATERIAL RECEIPT DETAILS VIEW ALLOCATION REPORT AP VIEW ALLOCATION REPORT AR | ISSUE | NYT |  | PRAVEEN
62 | 2025-01-08 | THIS SERVICE REQUEST VISIBLE IN CENTRA - HQ, BUT IT MISSING IN THE CENTRA - REGION R1. | HQOW / ROW | SALES MANAGEMENT | DELIVERY ORDER CONFIRM | ISSUE | NYT |  | PRAVEEN
63 | 2025-01-17 | 1. LOGIN REGION BANK NAMES ONLY SHOULD SHOW IN “BANK ACCOUNT” PARAMETER. REPORT : UNALLOCATED AR&AP PAYMENT REPORT | HQOW / ROW | ACCOUNTING MANAGEMENT | UNALLOCATED AR&AP PAYMENT REPORT | ISSUE | NYT |  | MANJULA
64 | 2025-01-17 | UNALLOCATED INVOICES MISSING IN ROW. | HQOW / ROW | ACCOUNTING MANAGEMENT |  | ISSUE | NYT |  | MANJULA
65 | 2025-01-17 | 1. LOGIN REGION BANK NAMES ONLY SHOULD SHOW IN “BANK ACCOUNT” PARAMETER. 2. LOGIN REGION TRANSACTION ONLY SHOULD SHOW IN UNRECONCILED PAYMENTS. CURRENCY THIS REPORT SHOW ALL THE REGION TRANSACTION. | HQOW / ROW | ACCOUNTING MANAGEMENT | UNRECONCILED PAYMENTS | ISSUE | NYT |  | MANJULA
66 | 2025-01-17 | MASTER INVENTORY PACKAGE REPORT SHOW DUPLICATE IN HQOW AND ROW. | HQOW / ROW | INVENTORY MANAGEMENT | MASTER INVENTORY PACKAGE REPORT | ISSUE | NYT |  | MANJULA
67 | 2025-01-17 | INVENTORY VALLUATION REPORT MISSING IN ROW. | HQOW / ROW | INVENTORY MANAGEMENT | INVENTORY VALLUATION REPORT | ISSUE | NYT |  | MANJULA
68 | 2025-01-20 | MANAGE PARTNER, BANK ACCOUNT TAB, BANK FILED FILED DROP DOWN SHOWS EMPTY VALUE | HQOW / ROW | MASTER MANAGEMENT | Mange partner screen bank column issue | ISSUE | NYT |  | GOBI
69 | 2025-01-20 | VENDOR INFO LINE ISSUE | HQOW / ROW | MASTER MANAGEMENT | VENDOR | ISSUE | NYT |  | GOBI
70 | 2024-01-20 | WHILE OPENING DEPARTMENT 500 SQL EXCEPTION SHOWING | HQOW | MASTER MANAGEMENT | DEPARTMENT | ISSUE | NYT |  | SURYA | 401184
71 | 2025-01-20 | METRO TRANSFER CREATE BUTTON IS NOT ENABLE CENTRA ROW | ROW | INVENTORY MANAGEMENT | METRO TRANSFER | ISSUE | NYT |  | GOBI
72 | 2025-01-20 | EXTRA PRODUCT COLUMN IN CENTRA INVOICE(VENDOR) "GOODS RECEIVE ADVICE" PRINT FORMATE FOR AP INVOCIE DOCUMENT TYPE AND INSTEAD OF SHIPMENT NO ONLY SHIPMENT IS MENTIONED AND INSTEAD OF QTYCARTONCONVERT ,QUANTITY(CARTONS) IS MENTIONED. | ROW | PURCHASE MANAGEMENT | INVOICE (VENDOR) | ISSUE | NYT |  | SANTHOSH | 401185
73 | 2025-01-20 | TRANSACTION DATA NOT SHOWING IN GOODS RECEIVE ADVICE PRINT IN INVOICE(VENDOR) SCREEN FOR CUSTOM CLEARANCE INVOICE. | ROW | PURCHASE MANAGEMENT | INVOICE (VENDOR) | ISSUE | NYT |  | SANTHOSH | 401223
74 | 2025-01-20 | "LOAN PAID" CHECK BOX IS NOT AVAILBLE IN ROW BUT IT IS PRESENT IN CENTRA REGION (THIS BUTTON IS PRESENT IN HQOW SO THERE IS A CHANCE THAT IT IS NOT DISABLED IN CENTRA REGION) | ROW | PURCHASE MANAGEMENT | PAYMENT – AP | ISSUE | NYT |  | SANTHOSH | 401191
75 | 2025-01-21 | REPORT NAME : VENDOR LIST REPORT 1.“BRANCH” PARAMETER SHOW DUPLICATE IN BOTH HQ AND ROW. 2. TAX CODE COLUMN DUPLICATE IN VENDOR LIST REPORT-ROW 3. BRANCH COLUMN FONT SIZE ISSUE(FONT SIZE DIFFERENT COMPAR TO OTHER COLUMNS) IN VENDOR LIST REPORT (PDF FORMAT). | HQOW / ROW | PURCHASE MANAGEMENT | VENDOR LIST REPORT | ISSUE | NYT |  | MANJULA
76 | 2025-01-22 | BRANCH SHOULD NOT BE (*) AS DEFAULT | HQOW | ACCOUNTING MANAGEMENT | IMPORT DISCOUNT SCHEMA | ISSUE | NYT |  | VINESH
77 | 2025-01-22 | EXPENSE TYPE FILED TAB ISSUE | HQOW | MASTER MANAGEMENT | EXPENSE TYPE | ISSUE | NYT |  | GOBI
78 | 2025-01-22 | IMPORT FEE GROUP CENTRA ROW R1 CREATE BUTTON ISSUE | ROW | MASTER MANAGEMENT | IMPORT FEE GROUP | ISSUE | NYT |  | GOBI
79 | 2025-01-22 | RECEIPT NOTE-MR_VERSION1 PRINT FORMAT HAS EXTRA DATA | HQOW/ROW | PURCHASE MANAGEMENT | MATERIAL RECEIPT | ISSUE | NYT |  | SANTHOSH | 401198
80 | 2025-01-22 | CREATE RETURN LINES IS MISSING IN MATERIAL RECEIPT AUTHORIZATION SCREEN | HQOW/ROW | PURCHASE MANAGEMENT | MATERIAL RECEIPT AUTHORIZATION | ISSUE | NYT |  | SANTHOSH | 401199
81 | 2025-01-22 | MATERIAL RECEIPT MISSING PRINT FORMAT IN CENTRA HQ UM_GRN_HEADER_V MATERIAL RECEIPT AUTHORIZATION MISSING PRINT FORMAT IN CENTRA HQ UM_GRN_HEADER_V | HQOW/ROW | PURCHASE MANAGEMENT | MATERIAL RECEIPT/ MATERIAL RECEIPT AUTHORIZATION | ISSUE | NYT |  | SANTHOSH | 401200
82 | 2025-01-22 | MATERIAL RECEIPT AUTHORIZATION SCREEN IN HQ MISSING POSTED BUTTON | HQOW/ROW | PURCHASE MANAGEMENT | MATERIAL RECEIPT AUTHORIZATION | ISSUE | NYT |  | SANTHOSH | 401201
83 | 2025-01-22 | WHILE ZOOMING IN BUSINESS PARTNER IT REDIRECTS TO MANAGE PARTNER SCREEN. BUT IN ROW IT REDIRECTS TO BUSINESS PARTNER | HQOW/ROW | PURCHASE MANAGEMENT | PAYMENT AP | ISSUE | NYT |  | SANTHOSH | 401202
84 | 2025-01-22 | PARTNER ADDRESS IS NOT SHOWING IN PAYMENT - AP PAYMENT PRINT FORMAT | HQOW/ROW | PURCHASE MANAGEMENT | PAYMENT – AP | ISSUE | NYT |  | SANTHOSH | 401203
85 | 2025-01-22 | EXTRA TAB RMA TAX IN VENDOR RMA SCREEN. IT SHOULD ONLY SHOW IN HQ, BUT IT IS SHOWING IN REGION | HQOW/ROW | PURCHASE MANAGEMENT | VENDOR RMA | ISSUE | NYT |  | SANTHOSH | 401204
86 | 2025-01-23 | IMPORT ROLE DOESNT HAVE ANY BRANCH FILTER TO CHANGE READ/WRITE,ACTIVE FOR SPECIFIC BRANCH (ONLY CHANGES *) | HQOW/ROW | MASTER MANAGEMENT | IMPORT ROLE | ISSUE | NYT |  | VINESH
87 | 2025-01-23 | PRODUCT COSTS SCREEN COST DETAILS TAB CREATE ENABLE IN CENTRA HQOW 8182 PRODUCT COSTS SCREEN COST DETAILS TAB CREATE BUTTON NOT ENABLE IN HQOW | HQOW | MASTER MANAGEMENT | PRODUCT COST | ISSUE | NYT |  | GOBI
88 | 2025-01-23 | PURCHASE ORDER NOT LOADING IN VENDOR RMA SCREEN | HQOW/ROW | PURCHASE MANAGEMENT | VENDOR RMA | ISSUE | NYT |  | SANTHOSH | 401207
89 | 2025-01-24 | THERE IS A MISMATCH BETWEEN THE COLUMNS AND DATA IN THE PDF AND XLSX FORMAT. | HQOW/ROW | SALES MANAGEMENT | MASTER DEBIT (MTS) | ISSUE | NYT |  | PRAVEEN
90 | 2025-01-25 | DUPLICATE TAX ISSUE “1NPO2311-10136 ”WHEN IMPORT THE MULITIPLE NTA PO RECORDS IN CENTRA | HQOW | PURCHASE MANAGEMENT | IMPORT NTA PURCHASE ORDER | ISSUE | NYT |  | HARIHARAN
91 | 2025-01-25 | 1.RMA LINE FIELD IS NOT SHOWING IN LINE 2.RETURN TO VENDOR SHOWING POSTING BUTTON IN CENTRA REGION | HQOW/ROW | PURCHASE MANAGEMENT | RETURN TO VENDOR | ISSUE | NYT |  | SANTHOSH | 401210
92 | 2025-01-25 | COGS ADJUSTMENT – POSTING BUTTON SHOWING IN CENTRA REGION | HQOW/ROW | PURCHASE MANAGEMENT | COGS ADJUSTMENT | ISSUE | NYT |  | SANTHOSH | 401211
93 | 2025-01-25 | AP CREDIT MEMO DOC SEQUENCE IS WRONG IN CENTRA | HQOW/ROW | PURCHASE MANAGEMENT | INVOICE (VENDOR) | ISSUE | NYT |  | SANTHOSH | 401212
94 | 2025-01-27 | BANK ACCOUNT PARAMETER DROP DOWN NOT SHOWING PROPERLY. | HQOW | ACCOUNT MANAGEMENT | LIST OF PAYMENT VOUCHER | ISSUE | NYT |  | PRAVEEN
95 | 2025-01-27 | THIS SR IS MISSING. | HQOW | ACCOUNT MANAGEMENT | TB REPORT VAS | ISSUE | NYT |  | PRAVEEN
96 | 2025-01-28 | WAREHOUSE & LOCATORS NOT ABLE TO CREATE ROW | ROW | MASTER MANAGEMENT | WAREHOUSE & LOCATORS | ISSUE | NYT |  | GOBI | 401233 |  | Tickets Created Upto 96 SNO
97 | 2025-01-28 | 42015 - Issue of Accounting Date during import Closing Journal not wqorking CENTRA applications | HQOW | ACCOUNT MANAGEMENT | GL Journal | ISSUE | NYT |  | MANIRATHNAM | 401224
98 | 2025-01-28 | GL Journal line takking more time for open(Centra Takking 9 Sec, HQOW Takking 2 Sec Only) | HQOW | ACCOUNT MANAGEMENT | GL Journal | ISSUE | NYT |  | HARIHARAN
99 | 2025-01-28 | In Advance Search tab while filter using Documnet Status: below mentioned dropdown Parameters are Missing [ Transfered, Partial Transfer ] | HQOW | FAM | CIP Register | ISSUE | NYT |  | SURYA | 401230
100 | 2025-01-28 | Document Status Shows Empty after Completed Partially Transferd Transfer CIP to FA Document and [Prtical Transfer and Transfered] Both status are not updated in the CIP Register Document CIP Register: CI2501-10402 Transfer CIP to FA: TR2501-10402 Transfer CIP to FA: TR2501-10403 | HQOW | FAM | CIP Register | ISSUE | NYT |  | SURYA | 401231
101 | 2025-01-28 | 1) Import NTA Goods Receipt Process Popup window shows empty branch value(Set Default Ho chi minh) 2) Goods Receipt Screen “Reference Order” Field show empty value(Should show PO Document) 3) Goods Receipt Screen “Date ordered” field shows read only(It should be editable after imported) | HQOW | PURCHASE MANAGEMENT | GOODS RECEIPT | ISSUE | NYT |  | HARIHARAN
102 | 2025-01-29 | NTA RECIEPT ALLOCATION SCREEN WRITE OFF ALLOCATION NOT PROPERLY WORKED | HQOW | SALES MANAGEMENT | NTA RECIEPT ALLOCATION | ISSUE | NYT |  | GOBI | 401240
103 | 2025-01-29 | NET OFF RECIEPT AND NET OFF ALLOCATION NEGIATIVE AMOUNTS ALLOCATION NOT PROPERLY WORKED | HQOW | SALES MANAGEMENT | NET OFF ALLOCATION | ISSUE | NYT |  | GOBI | 401241

## 401042
Import DMS Partner
108991788 | CHA GOO CO LTD | HCL | Centec Tower | Ho Chi Minh | Ho Chi Minh Vietnam | 6008298 | 9740421259 | IS | SM | 309129419 | 12ND | Price list for Channel | DNA | None | 100000 | 110001 | M&FS | N | N | H | 2000000 | Y | P.Thu KH (trade) | ART | Y | Y | CASH | Y | Y | N | 1000102
Manage Partner Search Key | 108991788