## Sheet1
ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Estimate Hours | Hours Spent | Stage | Target version | Progress
__export__.project_task_400396_5a8a13f0 | NGERP HQOW CENTRA | #400396 - Sales order screens after imported prom order created & updated by showing SuperUser it will show System in draft status of SO | Yogan P | Bugs | 2024-09-27 |  |  | 2024-12-02 18:24 | 0 | 0 | Resolved |  | 0
__export__.project_task_399997_29a84935 | NGERP HQOW CENTRA | #399997 - IMPORT Screens Issues | Manjula D | Bugs | 2024-07-08 |  |  | 2024-11-11 12:05 | 0 | 2 | Resolved |  | 0
__export__.project_task_399847_caa64ee1 | NGERP HQOW CENTRA | #399847 - promotion unique reference SO transactions not import properly showing error | Mohideen Imthiaz S | Bugs | 2024-08-01 |  |  | 2024-11-04 18:18 | 0 | 2 | Resolved |  | 0
__export__.project_task_399844_4692a782 | NGERP HQOW CENTRA | Customer No salaes report missing some column's compar to AWS Centra and AWS R1 | Selvakumar S | Bugs | 2024-07-19 |  |  | 2024-11-04 17:34 | 0 | 0 | Resolved |  | 0
__export__.project_task_399830_bae74849 | NGERP HQOW CENTRA | 3A Channel, Customer code column values shows empty. | Sathish K | Bugs | 2024-11-04 |  |  | 2024-11-04 14:21 | 0 | 18 | Resolved |  | 0
__export__.project_task_399537_cec99a19 | NGERP HQOW CENTRA | Sales order DSO case not working when swtich login to different region. | Yogan P | Bugs | 2024-10-15 |  |  | 2024-10-15 15:38 | 0 | 0 | Resolved |  | 0
__export__.project_task_400144_8d4d3711 | NGERP HQOW CENTRA | Depreciation GL Header and line contain extra unused columns. | Yogan P | Bugs | 2024-11-21 |  |  | 2024-11-21 16:02 | 0 | 2 | Resolved |  | 0
__export__.project_task_400437_a6675aac | NGERP HQOW CENTRA | #400437 - Should allow to reverse trade transaction in centra regions (copy) | Sethupathy A | Bugs | 2024-11-26 |  |  | 2024-12-05 17:49 | 0 | 0 | Resolved |  | 0
__export__.project_task_400072_db1614fe | NGERP HQOW CENTRA | #400072 - Trial Balance Reports Job process after check report showing multiple time same data centra applications issues | Thinesh Raajan S | Bugs | 2024-08-02 |  |  | 2024-11-12 17:19 | 0 | 5 | Resolved |  | 0
__export__.project_task_400430_a6fe72b9 | NGERP HQOW CENTRA | #400430 - Import DMS Order schedulerProcess Not propely showing msg | Yogan P | Bugs | 2024-08-06 |  |  | 2024-12-04 16:00 | 0 | 0 | Resolved |  | 0
__export__.project_task_399900_fe5d7b1c | NGERP HQOW CENTRA | List of Commercial discount report not working in Centra HQ | Kishore R | Bugs | 2024-08-10 |  |  | 2024-11-05 16:27 | 0 | 0 | Resolved |  | 0
__export__.project_task_398060_284bf0a7 | NGERP HQOW CENTRA | Import Payment(HSBC) ACK | Thinesh Raajan S | Bugs | 2024-08-07 |  |  | 2024-08-09 15:43 | 0 | 2 | Resolved |  | 0
__export__.project_task_400431_f341035d | NGERP HQOW CENTRA | #400431 - NTA Payment shows error during import it will allow to create&complete payment by manually | Thinesh Raajan S | Bugs | 2024-11-22 |  |  | 2024-12-04 18:03 | 0 | 0 | Resolved |  | 0
__export__.project_task_400427_38d069b0 | NGERP HQOW CENTRA | CIP Resgiter import untick FAM Records in HQ Centra. | Sridhar S | Bugs | 2024-11-22 |  |  | 2024-12-04 11:08 | 0 | 0 | Resolved |  | 0
__export__.project_task_399547_09fc59cc | NGERP HQOW CENTRA | Attribute set instance field performance issue in All transaction screen. | Sathish K | Bugs | 2024-10-17 |  |  | 2024-10-17 12:01 | 0 | 1 | Resolved |  | 0
__export__.project_task_400405_93f72b50 | NGERP HQOW CENTRA | Import FA Register imports unticked FAM NTA AP invoice records. | Sridhar S | Bugs | 2024-08-07 |  |  | 2024-12-03 15:21 | 0 | 0 | Resolved |  | 0
__export__.project_task_399620_d2887c86 | NGERP HQOW CENTRA | Master Balance by Customer (Monthly) - Report loading continuously | Thinesh Raajan S | Bugs | 2024-07-23 |  |  | 2024-10-21 18:01 | 0 | 3 | Resolved |  | 0
__export__.project_task_400230_de77ab96 | NGERP HQOW CENTRA | Master Balance by Customer (Daily) - ROW alignment issue | Yogan P | Bugs | 2024-07-23 |  |  | 2024-11-27 17:31 | 0 | 0 | Resolved |  | 0
__export__.project_task_400174_b1ee5ad8 | NGERP HQOW CENTRA | #400174 - Job roload completed for um_rv_bpartnerhistory_transaction_mv, so report show missing data | Thinesh Raajan S | Bugs | 2024-07-20 |  |  | 2024-11-25 12:37 | 0 | 5 | Resolved |  | 0