## Report (hidden)
# | SERVICE BUNDLES | SERVICE REQUEST -MACRO | SERVICE REQUEST -MICRO | HQ/ROW | PARAMETERS | DATA LOADING(PARAMETER WISE) | PRINT FORMAT | PDF FORMAT | XLSX FORMAT | PERIOD | PERFORMANCE-PDF | PERFORMANCE-XlSX | COLUMNS(AWS & CENTRA) | DATA CHECK | OVERALL STATUS | REMARK | COMMENT | TESTED BY | QA APPROVED BY | QA TIME | TICKET ID
1 | Sales Management | List of Commercial Discount report | List of Commercial Discount report | ROW | PASS | PASS | PASS | PASS | PASS | 10 Days | Time – 20 Sec | Time -5 Sec | PASS | New Data – PASS | PASS |  |  | Hari
2 | Purchase Management | Master NTA PO Report | Master NTA PO Report | HQOW | PASS | PASS | PASS | PASS | PASS | 1 Month | Time -8 Sec | Time -5 Sec | PASS | New Data – PASS | PASS |  |  | Hari
3 | Purchase Management | Master NTA PO Change List | Master NTA PO Change List | HQOW | PASS | PASS | PASS | PASS | PASS | 1 Day | Time -1 Min | Time -5 Sec | PASS | New Data – PASS | PASS |  |  | Hari |  | 15 Mins
4 | Master Management | Master Customer Change List_InDirect | Master Customer Change List_InDirect | ROW | PASS | FAIL | PASS | PASS | PASS | 2 Days | Time -1 Min | Time -1 Min | PASS | New Data – Fail | FAIL | 397183 |  | Hari
5 | Master Management | Master Customer Change List_Direct | Master Customer Change List_Direct | ROW | PASS | FAIL | PASS | PASS | PASS | 10 Days | Time -30 Sec | Time -15 Sec | PASS | New Data – Fail | FAIL | 397178 |  | Hari
6 | Master Management | Master Customer Change List_All | Master Customer Change List_All | ROW | PASS | PASS | PASS | PASS | PASS | 10 Days | Time -28 Sec | Time -10 sec | PASS | New Data – PASS | PASS |  |  | Hari
7 | Sales Management | MASTER CREDIT REPORT | MASTER CREDIT REPORT | HQOW + ROW | PASS | PASS | PASS | PASS | Unavailable | 10 Days | Time -30 Sec | Unavailable | PASS | New Data – PASS | PASS | 397167 |  | Hari
8 | Sales Management | MASTER BALANCE BY SALESMAN (MONTHLY) | MASTER BALANCE BY SALESMAN (MONTHLY) | HQOW + ROW | FAIL | FAIL | PASS | PASS | PASS | 2 Days | Time -30 Sec | Time -15 Sec | PASS | New Data – Fail | FAIL | 396873 |  | Hari
9 | Sales Management | MASTER BALANCE BY SALESMAN (DAILY) | MASTER BALANCE BY SALESMAN (DAILY) | HQOW + ROW | PASS | PASS | PASS | PASS | PASS | 10 Days | Time -1 Min | Time -20 Sec | PASS | New Data – PASS | PASS |  |  | Hari
10 | Sales Management | MASTER BALANCE BY Customer (MONTHLY) | MASTER BALANCE BY Customer (MONTHLY) | HQOW + ROW | PASS | FAIL | PASS | PASS | PASS | 11 Days | Time -30 Sec | Time -15 Sec | PASS | New Data – PASS | FAIL | 397172 |  | Hari
11 | Sales Management | MASTER BALANCE BY Customer (MONTHLY) | MASTER BALANCE BY Customer (MONTHLY) | HQOW + ROW | PASS | FAIL | PASS | PASS | PASS | 12 Days | Time -30 Sec | Time -15 Sec | PASS | New Data – PASS | FAIL | 397172 |  | Hari
12 | Sales Management | MASTER BALANCE BY Customer (DAILY) | MASTER BALANCE BY Customer (DAILY) | HQOW + ROW | PASS | FAIL | PASS | PASS | PASS | 2 Days | Time -10 Sec | Time -5 Sec | PASS | New Data – Pass | FAIL | 397170 |  | Hari
13 | Sales Management | Master AR Report VAS | Master AR Report VAS | HQOW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -10 Sec | Time -5 Sec | PASS | New Data – Pass | PASS | 397097 |  | Hari
14 | Sales Management | Master AR Report | Master AR Report | HQOW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -10 Sec | Time -5 Sec | PASS | New Data – Pass | PASS | 397096 |  | Hari
15 | Purchase Management | Master AP Report VAS | Master AP Report VAS | HQOW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -10 Sec | Time -5 Sec | PASS | New Data – Pass | PASS | 397050 |  | Hari
16 | Purchase Management | Master AP report | Master AP report | HQOW | PASS | PASS | PASS | PASS | PASS | 1 Day | Time -10 Sec | Time -5 Sec | PASS | New Data – Pass | PASS | 397049 |  | Hari
17 | Purchase Management | Master AP Payment Change List | Master AP Payment Change List | HQOW | PASS | PASS | PASS | PASS | PASS | 1 Day | Time -10 Sec | Time -5 Sec | PASS | New Data – Pass | PASS |  |  | Hari
18 | Master Management | MARKETING CAMPAIGN REPORT | MARKETING CAMPAIGN REPORT | HQOW | PASS | PASS | PASS | PASS | PASS | 4 Days | Time -10 Sec | Time -6 Sec | PASS | New Data – Pass | PASS |  |  | Hari
19 | Master Management | MARKETING CAMPAIGN CHANGE LIST | MARKETING CAMPAIGN CHANGE LIST | HQOW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -20 Sec | Time -10 sec | PASS | New Data – Pass | PASS |  |  | Hari
20 | Master Management | Mapping SGA Report | Mapping SGA Report | HQOW | PASS | PASS | PASS | PASS | PASS | As Of Date | Time -20 Min | Time -1 Min | PASS | New Data – Pass | PASS |  |  | Hari
21 | Master Management | MAPPING SGA CHANGE LIST REPORT | MAPPING SGA CHANGE LIST REPORT | HQOW | PASS | PASS | PASS | PASS | PASS | 1 Day | Time -20 Sec | Time -20 Sec | PASS | New Data – PASS | PASS |  |  | Hari |  | 19 Mins
22 | Master Management | Mapping HFM Change List Report | Mapping HFM Change List Report | HQOW | PASS | PASS | PASS | PASS | PASS | 1 Day | Time -30 Sec | Time -20 Sec | PASS | New Data – PASS | PASS |  |  | Hari |  | 15 Mins
23 | Master Management | Mapping D11 Change List report | Mapping D11 Change List report | HQOW | PASS | PASS | PASS | PASS | PASS | 1 Day | Time -15 Sec | Time -10 sec | PASS | New Data – PASS | PASS |  |  | Hari |  | 15 Mins
24 | Purchase Management | Loan Report | Loan Report | HQOW | PASS | PASS | PASS | PASS | PASS | 1 Day | Time -15 Sec | Time -10 sec | PASS | Not used – Report | PASS | 397105 |  | Hari |  | 15 Mins
25 | Sales Management | List of Promotion Sales-Package | List of Promotion Sales-Package | HQOW | PASS | PASS | PASS | PASS | PASS | 1 Day | Time -20 Sec | Time -20 Sec | PASS | New Data – PASS | PASS |  |  | Hari |  | 10 Mins
26 | Sales Management | List of Promotion Sales Gift | List of Promotion Sales Gift | HQOW | PASS | FAIL | PASS | PASS | PASS | 2 Days | Time -5 Sec | Time -3 Sec | FAIL | New Data – Fail | FAIL |  |  | Hari
27 | Sales Management | List of Promotion Sales | List of Promotion Sales | HQOW | PASS | FAIL | PASS | PASS | PASS | 1 Month | Time -5 Sec | Time -3 Sec | FAIL | New Data – Fail | FAIL |  |  | Hari |  | 25 Mins |  | 396948
28 | Sales Management | LIST OF PAYMENT VOUCHER | LIST OF PAYMENT VOUCHER | HQOW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -5 Sec | Time -3 Sec | PASS | New Data – PASS | PASS | 397072 |  | Hari
29 | Sales Management | List of Payment Summary Report | List of Payment Summary Report | HQOW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -5 Sec | Time -3 Sec | PASS | New Data – PASS | PASS | 397069 |  | Hari |  |  |  | 396863
30 | Sales Management | List Of Invoice Written To Be | List Of Invoice Written To Be | HQOW | PASS | PASS | PASS | PASS | PASS | 1 Month | Time -5 Sec | Time -3 Sec | PASS | Not used – Report | PASS |  |  | Hari |  |  |  | 396861
31 | Purchase Management | List of Import GRN | List of Import GRN | HQOW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -5 Sec | Time -3 Sec | PASS | New Data – PASS | PASS | 397065 |  | Hari
32 | Purchase Management | List Of GRN By Company | List Of GRN By Company | HQOW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -20 Sec | Time -15 Sec | PASS | New Data – PASS | PASS | 397046 |  | Hari
33 | Purchase Management | List Of GRN By Branch | List Of GRN By Branch | HQOW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -20 Sec | Time -15 Sec | PASS | New Data – PASS | PASS | 397047 |  | Hari
34 | Sales Management | List of Goods Returned-Pack | List of Goods Returned-Pack | HQOW | FAIL | PASS | PASS | PASS | PASS | 2 Days | Time -20 Sec | Time -15 Sec | PASS | New Data – Fail | FAIL | 397194 |  | Hari
35 | Sales Management | List of Goods Returned | List of Goods Returned | HQOW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -20 Sec | Time -15 Sec | PASS | New Data – PASS | FAIL | 397056 | Job fail | Hari
36 | Inventory Management | List of Goods issuing Note - Branch Transfer | List of Goods issuing Note - Branch Transfer | HQOW | PASS | PASS | PASS | PASS | PASS | 3 Days | Time -20 Sec | Time -15 Sec | Report not found | Report not found | PASS |  |  | Hari
37 | Inventory Management | List Of Goods Issue Note | List Of Goods Issue Note | HQOW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -5 Sec | Time -3 Sec | PASS | New Data – PASS | PASS | 397078 |  | Hari
38 | Purchase Management | List Of GIT Import | List Of GIT Import | HQOW | PASS | PASS | PASS | PASS | PASS | 1 Day | Time -29 Sec | Time -25 Sec | PASS | New Data – PASS | PASS | 397044 |  | Hari
39 | Accoutinh Management | LIST OF GIT AND ACCURAL GIFT | LIST OF GIT AND ACCURAL GIFT | HQOW | PASS | FAIL | PASS | PASS | PASS | 1 Month | Time -29 Sec | Time -25 Sec | PASS | FAIL | FAIL |  | 396798 | Hari
40 | sales Management | List of Discount Invoice Report | List of Discount Invoice Report | HQOW | PASS | FAIL | PASS | PASS | PASS | 1 Month | Time -35 Sec | Time -30 Sec | PASS | FAIL | FAIL |  | 396784 | Hari |  | 30 Mins
41 | sales Management | LIST OF COMMERCIAL DISCOUNT | LIST OF COMMERCIAL DISCOUNT | HQOW + ROW | PASS | PASS | PASS | PASS | PASS | 2 Month | Time -35 Sec | Time -30 Sec | PASS | New Data – PASS | PASS | 397161 |  | Hari
42 | sales Management | Invoice VAT In | Invoice VAT In | HQOW | PASS | FAIL | PASS | PASS | PASS | 10 Days | Time –3 Sec | Time – 2 Sec | PASS | FAIL | FAIL |  | 396770 | Hari
43 | sales Management | Invoice Status Report | Invoice Status Report | HQOW | PASS | FAIL | PASS | PASS | PASS | 10 Days | Time – 5 Sec | Time – 4 Sec | PASS | New Data – Fail | FAIL |  | 396754 | Hari |  | 10 Mins
44 | sales Management | INVOICE NOT REALIZED GAIN/LOSS | INVOICE NOT REALIZED GAIN/LOSS | HQOW | PASS | PASS | PASS | PASS | PASS | As Of Date | Time – 5 Sec | Time – 4 Sec | PASS | New Data – PASS | PASS |  |  | Hari
45 | sales Management | Invoice Detail & Margin | Invoice Detail & Margin | ROW | PASS | PASS | PASS | PASS | Fail | 10 Days | Time – 5 Sec | Time – 4 Sec | FAIL | New Data – PASS | FAIL | 397113 |  | Hari
46 | Inventory Management | INVENTRY IN GIFT | INVENTRY IN GIFT | HQOW | PASS | FAIL | PASS | PASS | PASS | 10 Days | Time – 5 Sec | Time – 4 Sec | FAIL | New Data – Fail | FAIL |  |  | Hari
47 | Inventory Management | Inventory Write off Report | Inventory Write off Report | HQOW | PASS | FAIL | PASS | PASS | PASS | 2 Days | Time -10 Sec | Time -5 Sec | FAIL | New Data – Fail | FAIL |  |  | Hari
48 | Inventory Management | INVENTORY VALUATION REPORT | INVENTORY VALUATION REPORT | HQOW + ROW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -10 Sec | Time -5 Sec | PASS | New Data – PASS | PASS | 397043 |  | Hari
49 | Inventory Management | Inventory Transaction Report | Inventory Transaction Report | HQOW | PASS | PASS | PASS | PASS | PASS | 3 Days | Time -10 Sec | Time -5 Sec | PASS | New Data – PASS | PASS | 397107 |  | Hari
50 | Inventory Management | INVENTORY SHELF LIFE REPORT | INVENTORY SHELF LIFE REPORT | HQOW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -10 Sec | Time -5 Sec | PASS | New Data – PASS | PASS | 397054 |  | Hari
51 | Inventory Management | INVENTORY PROVISION REPORT | INVENTORY PROVISION REPORT | HQOW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -10 Sec | Time -5 Sec | PASS | New Data – PASS | PASS | 397053 |  | Hari
52 | Inventory Management | INVENTORY OUT REPORT COMPANY | INVENTORY OUT REPORT COMPANY | HQOW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -10 Sec | Time -5 Sec | PASS | New Data – PASS | PASS | 397197 |  | Hari
53 | Inventory Management | INVENTORY OUT REPORT BRANCH | INVENTORY OUT REPORT BRANCH | HQOW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -10 Sec | Time -5 Sec | PASS | New Data – PASS | PASS | 396996 |  | Hari
54 | Inventory Management | INVENTORY OUT GIFT | INVENTORY OUT GIFT | HQOW | PASS | FAIL | PASS | PASS | PASS | 3 Days | Time -10 Sec | Time -5 Sec | PASS | New Data – Fail | FAIL | 397190 |  | Hari
55 | Inventory Management | INVENTORY INOUTBY COMPANY | INVENTORY INOUTBY COMPANY | HQOW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -10 Sec | Time -5 Sec | PASS | New Data – PASS | PASS | 397041 |  | Hari
56 | Inventory Management | INVENTORY INOUTBY BRANCH | INVENTORY INOUTBY BRANCH | HQOW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -10 Sec | Time -5 Sec | PASS | New Data – PASS | PASS | 397040 |  | Hari
57 | Inventory Management | INVENTORY INOUT GIFT | INVENTORY INOUT GIFT | HQOW | PASS | FAIL | PASS | PASS | PASS | 2 Days | Time -10 Sec | Time -5 Sec | FAIL | New Data – Fail | FAIL | 397196 |  | Hari
58 | Inventory Management | INVENTORY IN REPORT COMPANY | INVENTORY IN REPORT COMPANY | HQOW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -10 Sec | Time -5 Sec | PASS | New Data – PASS | PASS | 396995 |  | Hari
59 | Inventory Management | INVENTORY IN REPORT BRANCH | INVENTORY IN REPORT BRANCH | HQOW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -10 Sec | Time -5 Sec | PASS | New Data – PASS | PASS | 396994 |  | Hari
60 | Inventory Management | Inventory Card Report (Branch) | Inventory Card Report (Branch) | HQOW | PASS | PASS | PASS | PASS | PASS | 2 Days | Time -10 Sec | Time -5 Sec | PASS | New Data – PASS | PASS | 397067 |  | Hari
61 | Inventory Management | Inventory Card Report | Inventory Card Report | HQOW | PASS | PASS | PASS | PASS | PASS | 5 Days | Time -10 Sec | Time -5 Sec | PASS | New Data – PASS | PASS |  |  | Hari
62 | sales Management | Internal Revenue Report | Internal Revenue Report | HQOW | PASS | PASS | PASS | PASS | PASS | 2016 | Time -10 Sec | Time -5 Sec | PASS | Not used – Report | PASS | 397101 |  | Hari
63 | sales Management | Detail AR Report VAS | Detail AR Report VAS | HQOW | PASS | FAIL | PASS | PASS | PASS | 2 Days | Time -20 Sec | Time -10 sec | FAIL | New Data – Fail | FAIL | 396989 |  | Hari
64 | Sales Management | Detail AR report | Detail AR report | HQOW | PASS | FAIL | PASS | PASS | PASS | 2 Days | Time -20 Sec | Time -10 sec | FAIL | New Data – Fail | FAIL | 396988 |  | Hari
65 | Purchase Management | Detail AP Report VAS | Detail AP Report VAS | HQOW | PASS | FAIL | PASS | PASS | PASS | 2 Days | Time -20 Sec | Time -10 sec | PASS | New Data – Fail | FAIL | 396968 | New Data not loading the report after reload th e MV | Hari
66 | Purchase Management | Detail AP report | Detail AP report | HQOW | PASS | FAIL | PASS | PASS | PASS | 2 Days | Time -20 Sec | Time -10 sec | PASS | New Data – Fail | FAIL |  | New Data not loading the report after reload th e MV, NTA AP Invoice | Hari

## Master (hidden)
# | SERVICE BUNDLES | SERVICE REQUEST -MACRO | SERVICE REQUEST -MICRO | HQ/ROW | FIELD’S | TAB | CREATE | UPDATE/EDIT | DELETE | PERFORMANCE | OVERALL STATUS | REMARK | COMMENT | TEST DATA | TESTED BY | QA APPROVED BY | QA TIME | TICKET ID | START DATE | END DATE
77 | Master Management | Product Stage | Product Stage | HQOW + ROW | PASS | PASS | PASS | PASS | PASS | 5 Sec | PASS | [6 empty] | 397239 | 2024-07-24
20 | Master Management | Document Base Type | Document Base Type | HQOW + ROW | PASS | PASS | PASS | PASS | PASS | 6 Sec | PASS | [6 empty] | 397247 | 2024-07-24
21 | Master Management | Document Sequence | Define Document Sequence | HQOW + ROW | PASS | PASS | PASS | PASS | PASS | 5 Sec | PASS | [6 empty] | 397248 | 2024-07-24
22 | Master Management | Document Type | Define Document Type | HQOW + ROW + FAM | PASS | PASS | PASS | PASS | PASS | 3 Sec | PASS | [6 empty] | 397251 | 2024-07-24
24 | Master Management | GIFT PRODUCT | GIFT PRODUCT | HQOW + ROW | PASS | PASS | PASS | PASS | PASS | 3 Sec | PASS | [6 empty] | 397241 | 2024-07-24
25 | Master Management | GL Category | GL Category | HQOW + ROW | PASS | PASS | PASS | PASS | PASS | 3 Sec | PASS | [6 empty] | 397252 | 2024-07-24
101 | Master Management | User | Define User | HQOW + ROW | FAIL | FAIL | PASS | PASS | PASS | 3 Sec | FAIL |  | 2 Tab Missing , One Field missing |  | . |  |  | 397267 | 2024-07-25
82 | Master Management | RMA CATEGORY | RMA CATEGORY | HQOW + ROW | PASS | PASS | PASS | PASS | FAIL | 3 Sec | FAIL | [6 empty] | 397271 | 2024-07-25
83 | Master Management | Role | Define Role | HQOW + ROW | PASS | PASS | PASS | PASS | PASS | 3 Sec | PASS | [6 empty] | 397268 | 2024-07-25
84 | Master Management | Role | Define Role Access | HQOW + ROW | PASS | PASS | PASS | PASS | PASS | 3 Sec | PASS | [6 empty] | 397277 | 2024-07-25
85 | Master Management | Sales Channel | Sales Channel | HQOW + ROW | PASS | PASS | PASS | PASS | PASS | 3 Sec | PASS | [6 empty] | 397284 | 2024-07-25
86 | Master Management | Sales Person | Sales Rep Info | HQOW + ROW | PASS | PASS | PASS | PASS | PASS | 3 Sec | PASS | [6 empty] | 397289 | 2024-07-25
87 | Master Management | Sales Region Mapping | Define Sales Region | HQOW + ROW | PASS | PASS | PASS | PASS | PASS | 3 Sec | PASS | [6 empty] | 397290 | 2024-07-25
90 | Master Management | Scheduler | Email Configuration | HQOW + ROW | PASS | PASS | PASS | PASS | PASS | 3 Sec | PASS | [6 empty] | 397292 | 2024-07-25
91 | Master Management | Scheduler | Manage Scheduler | HQOW + ROW | PASS | PASS | PASS | PASS | PASS | 4 Sec | PASS | [6 empty] | 397296 | 2024-07-25
92 | Master Management | Session Audit | Session Audit | HQOW + ROW | PASS | PASS | PASS | PASS | PASS | 4 Sec | PASS | [6 empty] | 397301 | 2024-07-25
100 | Master Management | UOM Group | UOM Group | HQOW + ROW | FAIL | FAIL | PASS | PASS | PASS | 4 Sec | FAIL | [6 empty] | 397305 | 2024-07-25
109 | Master Management | Manage Item List | Manage Item List | ROW | PASS | PASS | PASS | PASS | PASS | 4 Sec | PASS | [6 empty] | 397309 | 2024-07-25
26 | Master Management | Group of Attributes | Group of Attributes | HQOW + ROW | PASS | PASS | PASS | PASS | PASS | 3 Sec | PASS | [6 empty] | 397311 | 2024-07-25
29 | Master Management | LOCATION | LOCATION | HQOW + ROW | PASS | PASS | PASS | PASS | PASS | 3 Sec | PASS | [6 empty] | 397312 | 2024-07-25
32 | Master Management | Manage Activity | Manage Activity | HQOW + ROW | PASS | PASS | PASS | PASS | PASS | 4 Sec | PASS | [6 empty] | 397314 | 2024-07-25
33 | Master Management | Manage Area Territory Mapping | Manage Area Territory Mapping | HQOW + ROW | PASS | PASS | PASS | PASS | PASS | 3 Sec | PASS | [6 empty] | 397316 | 2024-07-25
65 | Master Management | Product | Deactivate Product | HQOW + ROW | PASS | FAIL | PASS | PASS | PASS | 4 Sec | FAIL | [6 empty] | 397318 | 2024-07-25

## Print Format (hidden)
# | SERVICE BUNDLES | SERVICE REQUEST -MACRO | SERVICE REQUEST -MICRO | HQ/ROW | VERIFY PRINT FORMAT | VERIFY DATA LOADING | OVERALL STATUS | COMMENT | TEST DATA | TESTED BY | QA APPROVED BY | QA TIME | TICKET ID | START DATE | END DATE
21 | Sales Management | Manage DO | Manage DO Print – R6 -I | ROW | PASS | FAIL | FAIL | Print Format mismatch between Production and Centra |  | Hari |  | 10 Mins | 397341 | 2024-07-25 | 2024-07-25
22 | Sales Management | Manage DO | Manage DO Print – R6 -II | ROW | PASS | FAIL | FAIL | Print Format mismatch between Production and Centra |  | Hari |  | 10 Mins | 397351 | 2024-07-26 | 2024-07-26
23 | Sales Management | Manage DO | Manage DO Print – R6 -III | ROW | PASS | FAIL | FAIL | Print Format mismatch between Production and Centra |  | Hari |  | 10 Mins | 397357 | 2024-07-26 | 2024-07-26
24 | Sales Management | Manage DO | Manage DO Print – R6 -IV | ROW | PASS | FAIL | FAIL | Print Format mismatch between Production and Centra |  | Hari |  | 10 Mins | 397359 | 2024-07-26 | 2024-07-26
25 | Sales Management | Manage DO | Manage DO Print – R7 -I | ROW | PASS | FAIL | FAIL | Print Format mismatch between Production and Centra |  | Hari |  | 10 Mins | 397381 | 2024-07-26 | 2024-07-26
26 | Sales Management | Manage DO | Manage DO Print – R7 -II | ROW | PASS | FAIL | FAIL | Print Format mismatch between Production and Centra |  | Hari |  | 10 Mins | 397383 | 2024-07-26 | 2024-07-26
27 | Sales Management | Manage DO | Manage DO Print – R7 -III | ROW | PASS | FAIL | FAIL | Print Format mismatch between Production and Centra |  | Hari |  | 10 Mins | 397386 | 2024-07-26 | 2024-07-26
28 | Sales Management | Manage DO | Manage DO Print – R7 -IV | ROW | PASS | FAIL | FAIL | Print Format mismatch between Production and Centra |  | Hari |  | 10 Mins | 397388 | 2024-07-26 | 2024-07-26

## Jobs (hidden)
# | SERVICE BUNDLES | SERVICE REQUEST -MACRO | SERVICE REQUEST -MICRO | HQ/ROW | JOB DESCRIPTION | VERIFY SCHEDULER RUNNING | DATA CHECK | TIME TAKEN | OVERALL STATUS | COMMENT | TEST DATA | TESTED BY | QA APPROVED BY | QA TIME | TICKET ID | START DATE | END DATE
1 | Sales Managenment | Invoice Write Off Scheduler 1 | Invoice Write Off Scheduler 1 | ROW | Writeoff invoices for Amount <=1000 | PASS | PASS | 3 Sec | PASS |  |  | Hari |  | 30 Mins | 397430 | 2024-07-29 | 2024-07-29
2 | Sales Managenment | Invoice Write Off Scheduler 2 | Invoice Write Off Scheduler 2 | ROW | Writeoff invoices for Amount <=1000 | PASS | PASS | 3 Sec | PASS |  |  | Hari |  | 30 Mins | 397437 | 2024-07-29 | 2024-07-29
3 | Accounting Management | UnAlloPayAmtAcct | UnAlloPayAmtAcct | HQOW | UnAlloPayAmtAcct | PASS | PASS | 3 Sec | PASS |  |  | Hari |  | 1 Hour | 397450 | 2024-07-29 | 2024-07-29
4 | Accounting Management | UnAllocatedPayment | UnAllocatedPayment | HQOW | 1. UnAllocatedPayment is typically used to temporarily hold payments that haven’t been assigned to specific invoices or accounts. 2. It helps to keep track of funds untill they are properly allocated or not. | PASS | PASS | 3 Sec | PASS |  |  | Hari |  | 1 Hour | 397457 | 2024-07-29 | 2024-07-29
5 | Accounting Management | Reversal Accrual Monthly | Reversal Accrual Monthly | ROW | Create reversal entry for Accrual journals | PASS | PASS | 4 Sec | PASS |  |  | Hari |  | 1 Hour | 397475 | 2024-07-30 | 2024-07-30
6 | Accounting Management | GL Accrual Reversal Monthly | GL Accrual Reversal Monthly | ROW | Create reversal entry for Ratio adjustments journals | PASS | PASS | 5 Sec | FAIL |  |  | Hari |  | 1 Hour | 397478 | 2024-07-30 | 2024-07-30
7 | Accounting Management | GL Detail | GL Detail | HQOW | GL Detail refers general ledger. It include individual entries for things like sales, purchases, expenses, and other financial activities. | PASS | PASS | 5 Sec | PASS |  |  | Hari |  | 1 Hour | 397483 | 2024-07-30 | 2024-07-30
8 | Accounting Management | GL Detail CHILD (It will run auto after parent job) | GL Detail CHILD (It will run auto after parent job) | HQOW | GL Detail refers general ledger. It include individual entries for things like sales, purchases, expenses, and other financial activities. | PASS | PASS | 5 Sec | PASS |  |  | Hari |  | 1 Hour | 397484 | 2024-07-30 | 2024-07-30
9 | Accounting Management | ViewAllocation | ViewAllocation | HQOW | 1. ViewAllocation – helps to view how funds are distributed across various categories or accounts. 2. This report helps to know the payments assigned to specific invoices or accounts. | PASS | PASS | 5 Sec | PASS |  |  | Hari |  | 1 Hour | 397485 | 2024-07-30 | 2024-07-30
10 | Accounting Management | BpartnerHistory_Inout | BpartnerHistory_Inout | HQOW | BpartnerHistory_Inout record hepls in documenting all significant interactions, transactions, communications, and changes over time. | PASS | PASS | 5 Sec | PASS |  |  | Hari |  | 1 Hour | 397486 | 2024-07-30 | 2024-07-30
11 | Masters | CUSTOMERSERVICEKPI | CUSTOMERSERVICEKPI | HQOW | CUSTOMERSERVICEKPI- It refers Customer service key performance indicators and metrics used to evaluate the effectiveness of a company’s customer service KPI. It includes Customer satisfaction, Customer retention rate, Resolution time, etc. | PASS | PASS | 5 Sec | PASS |  |  | Hari |  | 1 Hour | 397500 | 2024-07-30 | 2024-07-30
12 | Masters | Bpartner History CHILD 1 | Bpartner History CHILD 1 | HQOW | 1. It refers to a record of interactions, transactions, and engagements with specific entities that the organization considers partners. 2. It helps to managing and maintaining Bpartners history. | PASS | PASS | 5 Sec | PASS |  |  | Hari |  | 30 Mins | 397648 | 2024-07-31 | 2024-07-31
13 | Masters | Bpartner History CHILD 2 | Bpartner History CHILD 2 | HQOW | 1. It refers to a record of interactions, transactions, and engagements with specific entities that the organization considers partners. 2. It helps to managing and maintaining Bpartners history. | PASS | PASS | 5 Sec | PASS |  |  | Hari |  | 30 Mins | 397672 | 2024-07-31 | 2024-07-31
14 | Inventory Management | Inventory Transaction | Inventory Transaction | HQOW | Inventory Transaction | PASS | PASS | 5 Sec | PASS |  |  | Hari |  | 30 Mins | 397737 | 2024-07-31 | 2024-07-31
15 | Synchronization Mgmt | Document Sequence update | Sync data cleanup | HQOW | Sync data cleanup 7 days once | PASS | PASS |  | PASS |  |  | Hari |  | 20 Mins | 397715 | 2024-08-01 | 2024-08-01
16 | Masters | Synch from HQ to Branches and FAM | Synch from HQ to Branches and FAM | HQOW | Masters(Product,Pricelist, Role etc) | PASS | PASS |  | PASS |  |  | Hari |  | 20 Mins | 397740 | 2024-08-01 | 2024-08-01
17 | Sales Managenment | DO Billing Cut-Off | DO Billing Cut-Off | ROW | Repost DO which are created after billing cutoff Unrevenuce account | PASS | PASS | 10 Sec | PASS |  |  | Hari |  | 2 Hours | 397748 | 2024-08-01 | 2024-08-01
18 | Sales Managenment | Invoice Billing Cut-Off | Invoice Billing Cut-Off | ROW | Repost Invoices which are created after billing cutoff | PASS | PASS | 10 Sec | FAIL |  |  | Hari |  | 2 Hours | 397766 | 2024-08-01 | 2024-08-01
19 | Masters | Document Sequence update | Document Sequence update | HQOW | Document sequence update First of Month | PASS | PASS | 20 Sec | PASS |  |  | Hari |  | 2 Hours | 397789 | 2024-08-01 | 2024-08-01
20 | Purchase Management | Import HSBC Acknowledgement | Import HSBC Acknowledgement | ROW | Complete payments based on Acknowledge received from HSBC | PASS | PASS | 20 Sec | PASS |  |  | Hari |  | 2 Hours | 397798 | 2024-08-01 | 2024-08-01
21 | Masters | SKU Contribution% Topline Scheduler | SKU Contribution% Topline Scheduler | HQOW | Allocate the SKU % in Campaign mapped Trade Products 1.Allocate the SKU % in Campaign mapped NTA Products. 2.Allocation calculated by Campaign formulas. | PASS | FAIL | 5 Sec | FAIL |  |  | Hari |  | 1 Hour | 398010 | 2024-08-08 | 2024-08-08
22 | Payment AP | Import HSBC Acknowledgement | Import HSBC Acknowledgement | HQOW | Import Ack file from HSBC to complete Payments 1.Import Ack file from HSBC to complete Payments 2.Compiere system will complelte the AP Payments automatically via xml file Acknowledgement. | PASS | PASS | 4 Sec | PASS |  |  | Hari |  | 2 Hours | 397798 | 2024-08-08 | 2024-08-08
23 | Payment AP | HSBC File Encryption | HSBC File Encryption | HQOW | Encrypt XML file for export into HSBC 1.Encrypt XML file for export into HSBC. 2.All The AP Payment sent to HSBC as xml file. | PASS | FAIL | 5 Sec | FAIL |  |  | Hari |  | 1 Hour | 398012 | 2024-08-08 | 2024-08-08
24 | Sales Managenment | Import DMS Sales Order | Export Reversed DMS Order | ROW | 2.Export Reversed DMS orders invoice to DMS system. 2.DMS get the data from ROW for Reversed invoices. | HOLD | HOLD | 5 Sec | FAIL |  |  | Hari |  | 30 Mins | 398553 | 2024-08-14 | 2024-08-14

## Integration
# | SERVICE BUNDLES | SERVICE REQUEST -MACRO | SERVICE REQUEST -MICRO | HQ/ROW | VERIFY PROCESS | DATA CHECK | TIME TAKEN | OVERALL STATUS | COMMENT | 21889.1 | TESTED BY | QA APPROVED BY | QA TIME | TICKET ID | START DATE | END DATE
1 | IMPORT & CALLOUT & EXPORT | EXPORT MARKETING CAMPAIGN - DMS | EXPORT MARKETING CAMPAIGN - DMS | HQOW
2 | IMPORT & CALLOUT & EXPORT | EXPORT PRICE - DMS | EXPORT PRICE - DMS | HQOW | Pass | Pass |  | Pass |  | Price list : Price list for BV Phu San Ha Noi00 NAME: Price list for BV Phu San Ha Noi 01/01/20230 Product Code: 35016 | Manirathnam
3 | IMPORT & CALLOUT & EXPORT | EXPORT PRODUCT - DMS | EXPORT PRODUCT - DMS | HQOW | Pass | Pass |  | Pass |  | Product Search key: 10034 Updated local list no from this empty to 100P776571134134 | Manirathnam
4 | IMPORT & CALLOUT & EXPORT | EXPORT PRICE LIST | EXPORT PRICE LIST | HQOW | Pass | Pass |  | Pass |  | Price list name: Price list for BV Phu San Ha Noi to Price list for BV Phu San Ha Noi00 | Manirathnam
5 | IMPORT & CALLOUT & EXPORT | EXPORT SCHEDULED SHIPMENTS | EXPORT SCHEDULED SHIPMENTS | HQ/ROW
6 | IMPORT & CALLOUT & EXPORT | IMPORT ACTIVITY | IMPORT ACTIVITY | HQOW | Pass | Pass |  | Pass |  | Activity Search Key: ABR | Surya
7 | IMPORT & CALLOUT & EXPORT | IMPORT SUB ACTIVITY | IMPORT SUB ACTIVITY | HQOW | Pass | Pass |  | Pass |  | Activity Search Key: D Sub Activity Search Key: 0008 | Surya
8 | IMPORT & CALLOUT & EXPORT | IMPORT ACTIVITY (MANUAL) | IMPORT ACTIVITY (MANUAL) | HQOW
9 | IMPORT & CALLOUT & EXPORT | IMPORT BUDGET | IMPORT BUDGET | HQOW | Pass | Pass |  | Pass |  | Budget Search Key: 2023APR568 | Surya
10 | IMPORT & CALLOUT & EXPORT | IMPORT BUDGET (MANUAL) | IMPORT BUDGET (MANUAL) | HQOW
11 | IMPORT & CALLOUT & EXPORT | IMPORT BUDGET PRODUCT GROUP | IMPORT BUDGET PRODUCT GROUP | HQOW | Pass | Pass |  | Pass |  | Budget Search Key: ETCSF2018 Sub Budget Search Key: 007226 Ammount: 64.826,00 Commited Ammount: 21.889,10 | Surya
12 | SALES MANAGEMENT | TMS INTERFACE LOG | TMS INTERFACE LOG | ROW
13 | MASTER MANAGEMENT | TMS PROGRAM MAPPING | TMS PROGRAM MAPPING | HQOW
14 | IMPORT & CALLOUT & EXPORT | IMPORT BUSINESS PARTNER | IMPORT BUSINESS PARTNER | HQ/ROW
15 | IMPORT & CALLOUT & EXPORT | IMPORT PROPOSAL | IMPORT PROPOSAL | HQOW | Pass | Pass |  | Pass |  | Proposal Search Key: S65951 | Surya
16 | IMPORT & CALLOUT & EXPORT | IMPORT PROPOSAL (MANUAL) | IMPORT PROPOSAL (MANUAL) | HQOW
17 | IMPORT & CALLOUT & EXPORT | IMPORT PROPOSAL PRODUCT GROUP | IMPORT PROPOSAL PRODUCT GROUP | HQOW
18 | IMPORT & CALLOUT & EXPORT | IMPORT PROPOSAL SKU | IMPORT PROPOSAL SKU | HQOW
19 | IMPORT & CALLOUT & EXPORT | IMPORT RECOMMENDED SHIPMENT | IMPORT RECOMMENDED SHIPMENT | HQOW
20 | IMPORT & CALLOUT & EXPORT | IMPORT SUB ACTIVITY | IMPORT SUB ACTIVITY | HQOW | Pass | Pass |  | Pass |  | DM,998,LAPTOP/PRINTER/DATA MAINTAINANCE | Surya
21 | IMPORT & CALLOUT & EXPORT | IMPORT SUB BUDGET | IMPORT SUB BUDGET | HQOW | Pass | Pass |  | Pass |  | Budget Search Key: BUD361 Sub Budget Search key: SB361 | Surya
22 | IMPORT & CALLOUT & EXPORT | IMPORT SUB PROPOSAL | IMPORT SUB PROPOSAL | HQOW | Pass | Pass |  | Pass |  | Proposal Search Key: S65950 Sub Proposal Search Key: 3WNTCPA25581P025 | Surya
23 | IMPORT & CALLOUT & EXPORT | EXPORT SO DETAIL | EXPORT SO DETAIL | ROW |  |  |  |  | SYN_SALE_ORDER_STATUS: Pass SYN_SALE_ORDER_DETAIL: Pass SYN_SO: Fail | SO DOC NUM: R2 CTH: 2SO32501-10016, 2SO32501-10017, 2SO32501-10018 R1 HCM: 1S2SO32501-10513, 1S2SO32501-10512, 1S2SO32501-10514 DO DOC NUM: R2 CTH: 2DO2501-10001, 2DO2501-10002, 2DO2501-10003 R1 HCM: 1DO2501-10101, 1DO2501-10102, 1DO2501-10103 Invoice Doc Num: R2 CTH: 2AR12501-10001, 2AR12501-10002, 2AR12501-10003 R1 HCM: 1AR12501-10101, 1AR12501-10102, 1AR12501-10103 | Surya
24 | IMPORT & CALLOUT & EXPORT | IMPORT DMS BUSINESS PARTNER | IMPORT DMS BUSINESS PARTNER | ROW |  |  |  |  | Unexpected SQL Exception - Please check server log for details |  | Surya
25 | IMPORT & CALLOUT & EXPORT | IMPORT DMS ORDER | IMPORT DMS ORDER | ROW |  |  |  |  | 1. Doc seq not working | 02/01/2025 failed Import Promotion Orders is showing “Could not Save the order and java.lang.nullpointer exception” error on Temp Screen issue ------------------------ Surya 03/01/2025 So Doc num: 1SO32412-13152, 1SO32412-13153 Do Doc num: 1DO2412-12602, 1DO2412-12603 Invocie Doc num: 1AR12412-12802, 1AR12412-12803 -------------------------------- | Surya / Manirathnam
26 | IMPORT & CALLOUT & EXPORT | IMPORT DMS SALES PERSON PROCESS | IMPORT DMS SALES PERSON PROCESS | ROW | Pass | Pass |  | Pass |  | 14587548_3,SS SM QA JAN,,2025-02-02 00:00:00,107709040054,,10933509304,sssm.qajan@test.com,Y,1000102 | Surya
27 | IMPORT & CALLOUT & EXPORT | IMPORT SALES ORDER - DMS | IMPORT SALES ORDER - DMS | ROW
28 | PURCHASE MANAGEMENT | HSBC FILE ENCRYPTION | HSBC FILE ENCRYPTION | HQOW
29 | SALES MANAGEMENT | EMAIL NOTIFICATION TO SALESMEN ABOUT SUCCESS/FAILURE IMPORTED SOS | EMAIL NOTIFICATION TO SALESMEN ABOUT SUCCESS/FAILURE IMPORTED SOS | ROW
30 | PURCHASE MANAGEMENT | IMPORT RS PURCHASE | IMPORT RS PURCHASE | ROW | PASS | PASS |  | PASS |  |  | MANIRATHNAM
31 | PURCHASE MANAGEMENT | IMPORT RS PURCHASE
32 | INVENTORY MANAGEMENT | IMPORT RS TRANSFER | IMPORT RS TRANSFER | ROW | PASS | PASS |  | PASS |  |  | MANIRATHNAM

## Import & Export (hidden)
# | SERVICE BUNDLES | SERVICE REQUEST -MACRO | SERVICE REQUEST -MICRO | HQ/ROW | VERIFY FORMAT | VERIFY TEMP SCREEN | DATA IN MAIN SCREEN | SINGLE DATA IMPORT | MULTIPLE DATA IMPORT | TIME TAKKEN | OVERALL STATUS | COMMENT | TEST DATS | TESTED BY | QA APPROVED BY | QA TIME | TICKET ID | START DATE | END DATE
1 | Import & Callout & Export | Import Payment netoff | Import Payment netoff | HQOW | PASS | PASS | PASS | PASS | PASS | Single Data : 03 Sec Muliple Data(96) – 10 Sec | PASS | [5 empty] | 397923 | 2024-08-06 | 2024-08-06
2 | Import & Callout & Export | IMPORT STANDARD COST PRICE | IMPORT STANDARD COST PRICE | HQOW | PASS | PASS | PASS | PASS | PASS | Single Data : 03 Sec Muliple Data(20) – 8 Sec | PASS | [5 empty] | 397927 | 2024-08-06 | 2024-08-06
3 | Import & Callout & Export | Import Internal Transfer Invoice | Import Internal Transfer Invoice | ROW | PASS | PASS | FAIL | PASS | PASS | Single Data : 03 Sec Muliple Data(15) – 8 Sec | FAIL | Data showing read only |  |  |  |  | 397935 | 2024-08-06 | 2024-08-06
4 | Import & Callout & Export | Import Payment(HSBC) | Import Payment(HSBC) | ROW | PASS | FAIL | HOLD | HOLD | FAIL | HOLD | FAIL | Temp screen missing |  |  |  |  | 397939 | 2024-08-06 | 2024-08-06
5 | Import & Callout & Export | Import Products | Import Products | HQOW | Not Used |  |  | Not Used |  |  | Not Used | [6 empty] | 2024-08-06 | 2024-08-06
6 | Import & Callout & Export | IMPORT NTA GOODS RECEIPT | IMPROT NTA GOODS RECEIPT | HQOW | PASS | PASS | PASS | PASS | PASS | Single Data : 5 Sec Muliple Data(200) – 5 Min 20 Sec | PASS | [5 empty] | 397949 | 2024-08-07 | 2024-08-07
7 | Import & Callout & Export | Import FA Register | Import FA Register | FAM | PASS | FAIL | HOLD | FAIL | FAIL | HOLD | FAIL | [5 empty] | 397951 | 2024-08-07 | 2024-08-07
8 | Import & Callout & Export | Import CIP Register | Import CIP Register | FAM | PASS | PASS | PASS | PASS | PASS | Single Data : 3 Sec Muliple Data(3) – 5 Sec | PASS | [5 empty] | 397957 | 2024-08-07 | 2024-08-07

## TPP (hidden)
# | SERVICE BUNDLES | SERVICE REQUEST -MACRO | SERVICE REQUEST -MICRO | HQ/ROW | VERIFY CREATE | VERIFY UPDATE | VERIFY DELETE | VERIFY COMPLETE | VERIFY FIELD | VERIFY POSTING | VERIFY SCREEN PRINT | VERIFY VOID/REVERSE | VERIFY REVERSE DOCUMENT/ POSTING | OVERALL STATUS | COMMENT | TEST DATA | TESTED BY | QA APPROVED BY | QA TIME | TICKET ID | START DATE | END DATE
1 | Purchase Management | NTA Payment-AP | Create AP Payment | HQOW | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS |  |  | HARI |  | 1:30 Hour | 398049 | 2024-08-09 | 2024-08-09
2 | Purchase Management | NTA Payment-AP | Post Payment | HQOW | NP | NP | NP | NP | PASS | PASS | PASS | PASS | PASS | PASS |  |  | HARI |  | 1:30 Hour | 398057 | 2024-08-09 | 2024-08-09
3 | Purchase Management | NTA Purchase Order | Manage NTA Purchase Order | HQOW | PASS | PASS | PASS | PASS | FAIL | HOLD | PASS | PASS | NP | FAIL |  |  | HARI |  | 1:30 Hour | 398059 | 2024-08-09 | 2024-08-09
4 | Purchase Management | Payment Netoff | Post Net-Off Payment | HQOW | PASS | PASS | PASS | PASS | FAIL | HOLD | PASS | PASS | NP | FAIL |  |  | HARI |  | 1:30 Hour | 398065 | 2024-08-09 | 2024-08-09
5 | Sales Management | Proposal SKU | Proposal SKU | HQOW | PASS | PASS | PASS | NP | PASS | NP | PASS | NP | NP | PASS |  |  | HARI |  | 1:30 Hour | 398074 | 2024-08-09 | 2024-08-09
6 | Purchase Management | VAT Transfer (NTA) | Complete VAT Transfer – Update invoice | HQOW | PASS | PASS | PASS | PASS | PASS | PASS | PASS | NP | NP | PASS |  |  | HARI |  | 1:30 Hour | 398109 | 2024-08-12 | 2024-08-12
7 | Inventory Management | Stock take adjustment | Stock take adjustment | HQOW + ROW | PASS | PASS | PASS | PASS | PASS | PASS | PASS | NP | NP | PASS |  |  | HARI |  | 1:30 Hour | 398113 | 2024-08-12 | 2024-08-12
8 | Inventory Management | Stock take adjustment authorization | Stock take adjustment authorization | HQOW + ROW | NP | NP | NP | PASS | PASS | NP | PASS | NP | NP | PASS |  |  | HARI |  | 1:30 Hour | 398115 | 2024-08-12 | 2024-08-12
9 | FAM Management | Manage CIP Register | CIP Register | HQOW + FAM | PASS | PASS | PASS | FAIL | PASS | HOLD | HOLD | FAIL | NP | FAIL |  |  | HARI |  | 1:30 Hour | 398120 | 2024-08-12 | 2024-08-12
10 | FAM Management | Depreciation GL Mapping | Depreciation GL Mapping | HQOW + FAM | PASS | PASS | PASS | PASS | PASS | NP | NP | NP | NP | PASS |  |  | HARI |  | 1:30 Hour | 398126 | 2024-08-12 | 2024-08-12
11 | Purchase Management | Treasury File Encryption | Treasury File Encryption | HQOW | NP | NP | NP | NP | NP | NP | NP | NP | NP | PASS |  |  | HARI |  | 15 Min | 398472 | 2024-08-12 | 2024-08-12
12 | FAM Management | Posting CIP Transfer | Posting CIP Transfer | HQOW + FAM | NP | NP | NP | NP | NP | No posting | NP | NP | NP | PASS |  |  | HARI |  | 20 Min | 398488 | 2024-08-13 | 2024-08-13
13 | FAM Management | Manage FA Register | Manage FA Register | HQOW + FAM | PASS | PASS | PASS | PASS | FAIL | NP | NP | PASS | NP | FAIL |  |  | HARI |  | 1:30 Hour | 398497 | 2024-08-13 | 2024-08-13
14 | Inventory Management | Sending Branch Transfer | Sending Branch Transfer | HQOW + ROW | PASS | PASS | PASS | PASS | FAIL | PASS | PASS | PASS | NP | FAIL |  |  | HARI |  | 1:30 Hour | 398502 | 2024-08-13 | 2024-08-13
15 | FAM Management | FA Disposal & Write Off | FA Disposal & Write Off | HQOW + FAM | PASS | PASS | PASS | PASS | PASS | FAIL | NP | PASS | NP | FAIL |  |  | HARI |  | 1:30 Hour | 398505 | 2024-08-13 | 2024-08-13
16 | Purchase Management | AP Payment | AP Payment | HQOW + ROW | PASS | PASS | PASS | PASS | FAIL | PASS | NP | PASS | PASS | FAIL |  |  | HARI |  | 1:30 Hour | 398062 | 2024-08-13 | 2024-08-13
17 | Sales Management | Customer RMA Authorization | Customer RMA Authorization | HQOW + ROW | NP | PASS | PASS | PASS | FAIL | NP | NP | PASS | NP | FAIL |  |  | HARI |  | 1:30 Hour | 398523 | 2024-08-14 | 2024-08-14
18 | Sales Management | Customer Return | Customer Exchange (Same Price) | HQOW + ROW | FAIL | FAIL | FAIL | HOLD | HOLD | HOLD | HOLD | HOLD | HOLD | FAIL |  |  | HARI |  | 1:30 Hour | 398531 | 2024-08-14 | 2024-08-14
19 | Sales Management | Customer Return | Customer Exchange (different price) | HQOW + ROW | FAIL | FAIL | FAIL | HOLD | HOLD | HOLD | HOLD | HOLD | HOLD | FAIL |  |  | HARI |  | 1:00 Hour | 398531 | 2024-08-14 | 2024-08-14
20 | Purchase Management | COGS Adjustment | COGS Adjustment | HQOW | PASS | PASS | PASS | PASS | FAIL | PASS | NP | PASS | PASS | FAIL |  |  | HARI |  | 1:30 Hour | 398536 | 2024-08-14 | 2024-08-14
21 | Sales Management | Manage SO Campaigns | Manage SO Multi Campaigns | ROW | PASS | NP | NP | NP | PASS | NP | NP | NP | NP | PASS |  |  | HARI |  | 1:30 Hour | 398564 | 2024-08-14 | 2024-08-14
22 | Sales Management | Manage Attribute Combinations | Manage Attribute Combinations | ROW | PASS | PASS | PASS | NP | PASS | NP | NP | NP | NP | PASS |  |  | HARI |  | 1:00 Hour | 398570 | 2024-08-16 | 2024-08-16
1 | FAM Management | Create GL Journal | GL Journal | HQOW + FAM | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | NP | FAIL |  |  | HARI |  | 02:00 Hour | 398584 | 2024-08-16 | 2024-08-16
2 | FAM Management | GL Journal Authorization | GL Journal Authorization | HQOW + FAM | NP | PASS | PASS | PASS | PASS | PASS | PASS | PASS | NP | PASS |  |  | HARI |  | 1:00 Hour | 398590 | 2024-08-16 | 2024-08-16
3 | FAM Management | Auto Booking FA Disposal & Write Off | Auto Booking FA Disposal | FAM | NP | NP | NP | NP | NP | No posting | NP | NP | NP | Not used |  |  | HARI |  | 15 Min | 398591 | 2024-08-16 | 2024-08-16
4 | FAM Management | FA Depreciation monthly | FA Depreciation monthly | FAM | NP | FAIL | NP | NP | PASS | NP | NP | NP | NP | FAIL |  |  | HARI |  | 1:00 Hour | 398599 | 2024-08-16 | 2024-08-16
5 | Inventory Management | UnPack Package | Unpack Package | ROW | NP | NP | NP | FAIL | PASS | NP | NP | NP | NP | FAIL |  |  | HARI |  | 1:30 Hour | 398607 | 2024-08-19 | 2024-08-19
6 | Sales Management | Validate Import Proposal SKU | Validate Import Proposal SKU | HQOW | PASS | PASS | PASS | PASS | PASS | NP | NP | NP | NP | PASS |  |  | HARI |  | 1:30 Hour | 398608 | 2024-08-19 | 2024-08-19
7 | Inventory Management | Synch-in-Transit | Synch-in-Transit | ROW | PASS | PASS | PASS | FAIL | PASS | NP | NP | NP | NP | FAIL |  |  | HARI |  | 1:30 Hour | 398613 | 2024-08-19 | 2024-08-19
8 | Sales Management | Receivables Write Off | Write Off | HQOW | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS |  |  | HARI |  | 1:30 Hour | 398616 | 2024-08-19 | 2024-08-19
9 | Inventory Management | Manage Import Product Fee Alloc | Manage Import Product Fee Alloc | HQOW | PASS | PASS | PASS | FAIL | PASS | NP | PASS | NP | NP | FAIL |  |  | HARI |  | 1:00 Hour | 398618 | 2024-08-19 | 2024-08-19
10 | Sales Management | Sales Order | Consignment Type Order | HQOW + ROW | PASS | PASS | PASS | PASS | FAIL | PASS | FAIL | PASS | NP | FAIL | Before test this need fo fix consigment |  | HARI |  | 2:00 Hour | 398689 | 2024-08-21 | 2024-08-21
11 | Sales Management | Sales Order | Process Sales Order | ROW | HOLD | HOLD | HOLD | HOLD | FAIL | FAIL | FAIL | PASS | NP | FAIL |  |  | HARI |  | 2:00 Hour | 398688 | 2024-08-21 | 2024-08-21

## Form (hidden)
# | SERVICE BUNDLES | SERVICE REQUEST -MACRO | SERVICE REQUEST -MICRO | HQ/ROW | VERIFY PARAMETER | VERIFY FILTER | VERIFY SINGLE PROCESS | VERIFY MULTIPLE PROCESS | VERIFY FOOTER COLUMN | OVERALL STATUS | COMMENT | TEST DATA | TESTED BY | QA APPROVED BY | QA TIME | TICKET ID | START DATE | END DATE
1 | FORM | Batch Complete Commercial Discount | Batch Complete Commercial Discount | HQOW | PASS | PASS | PASS | PASS | FAIL | FAIL | Overhall converted amount value shows wrong |  | Hari |  | 2:00 | 398648 | 2024-08-20 | 2024-08-20
2 | FORM | Reject Commercial Discount | Reject Commercial Discount | HQOW | PASS | PASS | PASS | PASS | PASS | PASS |  |  | Hari |  | 26:00 | 398649 | 2024-08-20 | 2024-08-20
3 | FORM | Multi VAT Transfer | Multi VAT Transfer | HQOW | PASS | PASS | FAIL | FAIL | PASS | FAIL | Invoice not loading in Multi VAT Trasnfer form |  | Hari |  | 1:00 | 398656 | 2024-08-20 | 2024-08-20
4 | FORM | Generate Treasury Encryption | Generate Treasury Encryption | HQOW | PASS | PASS | FAIL | FAIL | PASS | FAIL | File not exported |  | Hari |  | 1:30 | 398669 | 2024-08-20 | 2024-08-20
5 | FORM | ExportBatch AP City Report | ExportBatch AP City Report | HQOW | PASS | PASS | PASS | PASS | PASS | PASS |  |  | Hari |  | 1:30 | 398676 | 2024-08-21 | 2024-08-21
6 | FORM | Import File Loader | Import File Loader | ROW | PASS | FAIL | PASS | PASS | FAIL | FAIL | Some formats missing |  | Hari |  | 1:30 | 398680 | 2024-08-21 | 2024-08-21
7 | FORM | System Cash Receipt By Salesman | System Cash Receipt By Salesman | ROW | PASS | FAIL | FAIL | FAIL | PASS | FAIL | Process not working |  | Hari |  | 1:30 | 398691 | 2024-08-22 | 2024-08-22
8 | FORM | Re-Print System Receipt By Salesman | Re-Print System Receipt By Salesman | ROW | PASS | PASS | FAIL | FAIL | PASS | FAIL | Process not working |  | Hari |  | 1:30 | 398698 | 2024-08-22 | 2024-08-22
9 | FORM | RePrint Picking List Summary | RePrint Picking List Summary | ROW | PASS | PASS | FAIL | FAIL | PASS | FAIL | Process not working |  | Hari |  | 1:30 | 398701 | 2024-08-22 | 2024-08-22
10 | FORM | Update Customer Confirmation | Update Customer Confirmation | ROW | PASS | PASS | PASS | PASS | PASS | PASS |  |  |  |  | 1:30 | 398705 | 2024-08-23 | 2024-08-23
11 | FORM | Update Invoice Details to TMS | Update Invoice Details to TMS | ROW | PASS | PASS | FAIL | FAIL | PASS | FAIL | Log not created |  | Hari |  | 1:30 | 398724 | 2024-08-23 | 2024-08-23
12 | FORM | Print Batch Invoice | Print Batch Invoice | ROW | PASS | FAIL | PASS | FAIL | PASS | FAIL | Multiple process fail |  | Hari |  | 1:30 | 398726 | 2024-08-23 | 2024-08-23
13 | FORM | Reject Approved Request | Reject Approved Request | ROW | PASS | Not used |  |  | Not used |  |  |  | Hari |  | 1:00 | 398749 | 2024-08-23 | 2024-08-23
14 | FORM | Update System ReceiptNo By Salesman | Update System ReceiptNo By Salesman | ROW | PASS | PASS | FAIL | FAIL | PASS | FAIL | Process not working |  | Hari |  | 1:30 | 398752 | 2024-08-26 | 2024-08-26
15 | FORM | CreateFromPOI | CreateFromPOI | ROW | PASS | PASS | PASS | PASS | PASS | PASS |  |  | Hari |  | 1:30 | 398753 | 2024-08-26 | 2024-08-26
16 | FORM | CreateFromInvoice | CreateFromInvoice | ROW | PASS | PASS | PASS | PASS | PASS | PASS |  |  | Hari |  | 1:30 | 398754 | 2024-08-26 | 2024-08-26
17 | FORM | CreateFromShipment | CreateFromShipment | ROW | PASS | PASS | PASS | PASS | PASS | PASS |  |  | Hari |  | 1:30 | 398760 | 2024-08-26 | 2024-08-26
18 | FORM | Generate Transport Manifest | Generate Transport Manifest | ROW | PASS | PASS | FAIL | FAIL | FAIL | FAIL | Process not working |  | Hari |  | 1:30 | 398769 | 2024-08-26 | 2024-08-26
19 | FORM | Print Batch DO | Print Batch DO | ROW | PASS | PASS | FAIL | FAIL | FAIL | FAIL | Form not released |  | Hari |  | 0:30 | 398521 | 2024-08-26 | 2024-08-26