## Sheet1
ID | Project | Title | Assigned to | ABCDE Type | Start Date | End date | UAT Release date | Created On | Created by | Estimate Hours | Hours Spent | End date | Tags | Stage | Target version | Progress | Name
__export__.project_task_401175_23e582fb | NGERP HQOW CENTRA | ACL Checklist QA Testing | Sridhar S | Bugs | 2024-12-10 |  | 2024-12-19 | 2025-01-27 10:28 | Manirathnam T | 0 | 35 |  | INTERNAL-AFTER-UAT-RELEASE | Reopened |  | 0
__export__.project_task_401018_41fc4c64 | NGERP HQOW CENTRA | NTA PO AND GR TRANASACTION DETAILS SHOULD NOT SHOW IN ROW. | Yogan P | Bugs | 2025-01-17 |  |  | 2025-01-17 11:21 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Resolved |  | 0 | Surya
__export__.project_task_401016_f91a1648 | NGERP HQOW CENTRA | LOGIN REGION TRANSACTION ONLY SHOULD SHOW IN TOTAL SALES (MTS) BY CUSTOMER. BUT CURRENCY REPORT SHOW ALL REGION DATA. | Mohideen Imthiaz S | Bugs | 2025-01-17 |  |  | 2025-01-17 11:16 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Reopened |  | 0
__export__.project_task_401012_7c265fb6 | NGERP HQOW CENTRA | SYSTEM COULD NOT ALLOW TO CREATE NEW CONSIGNMENT ORDER GIFT(CREATE NEW ICON DISABLE) | Yogan P | Bugs | 2024-12-17 |  |  | 2025-01-17 11:14 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401009_8985fa72 | NGERP HQOW CENTRA | ORDER TRANSACTIONS REPORT – THIS REPORT SHOW ALL THE REGION TRANSACTION'S. BUT IT SHOULD SHOW LOGIN REGION TRANSACTION'S DETAILS ONLY. | Mohideen Imthiaz S | Bugs | 2024-12-17 |  |  | 2025-01-17 11:09 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401017_8fb7feec | NGERP HQOW CENTRA | SHIPMENT DETAIL report issue | Yogan P | Bugs | 2025-01-17 |  |  | 2025-01-17 11:18 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Resolved |  | 0 | Surya
__export__.project_task_401007_e6c2ec13 | NGERP HQOW CENTRA | HQOW CENTRA - ACL Related bugs | Yogan P | Enhancement Request | 2025-01-17 |  |  | 2025-01-17 11:06 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | New |  | 0
__export__.project_task_401015_742d3da6 | NGERP HQOW CENTRA | CREATE BUTTON NOT WORKING | Yogan P | Bugs | 2024-12-17 |  |  | 2025-01-17 11:16 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401011_a191585e | NGERP HQOW CENTRA | Report ACL issue | Yogan P | Bugs | 2024-12-17 |  |  | 2025-01-17 11:13 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401231_c27d74b5 | NGERP HQOW CENTRA | Centra CIP Register document status issue | Sridhar S | Bugs | 2024-12-01 |  |  | 2025-01-28 18:49 | Manirathnam T | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401230_1d70a150 | NGERP HQOW CENTRA | In Advance Search tab while filter using Documnet Status: below mentioned dropdown Parameters are Missing | Sridhar S | Bugs | 2024-12-01 |  |  | 2025-01-28 18:45 | Manirathnam T | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_400865_d7acf9a0 | NGERP HQOW CENTRA | Confirm DMS Export Form Not showing in Centra ROW. | Yogan P | Bugs | 2025-01-03 |  |  | 2025-01-03 10:46 | Hariharan P | 0 | 1 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401244_8128d178 | NGERP HQOW CENTRA | Confirm DMS Export Form(ROW) Loading NTA Records. | Yogan P | Bugs | 2025-01-30 |  |  | 2025-01-30 12:54 | Hariharan P | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | New |  | 0
__export__.project_task_401246_7ecc4ff7 | NGERP HQOW CENTRA | Import Tally Sheet Temp screen taking a more time to open | Sethupathy A | Bugs | 2025-01-17 |  |  | 2025-01-30 16:01 | Hariharan P | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | New |  | 0
__export__.project_task_401214_bdad17b5 | NGERP HQOW CENTRA | THIS SR IS MISSING - TB REPORT VAS | Yogan P | Bugs | 2025-01-27 |  |  | 2025-01-27 17:05 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401213_45cc658b | NGERP HQOW CENTRA | BANK ACCOUNT PARAMETER DROP DOWN NOT SHOWING PROPERLY | Mohideen Imthiaz S | Bugs | 2025-01-27 |  |  | 2025-01-27 17:04 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401212_d8d5f668 | NGERP HQOW CENTRA | AP CREDIT MEMO DOC SEQUENCE IS WRONG IN CENTRA | Mohideen Imthiaz S | Bugs | 2025-01-27 |  |  | 2025-01-27 17:03 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Reopened |  | 0
__export__.project_task_401211_99a26e71 | NGERP HQOW CENTRA | COGS ADJUSTMENT – POSTING BUTTON SHOWING IN CENTRA REGION | Mohideen Imthiaz S | Bugs | 2025-01-27 |  |  | 2025-01-27 17:02 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401210_9a037bc3 | NGERP HQOW CENTRA | 1.RMA LINE FIELD IS NOT SHOWING IN LINE 2.RETURN TO VENDOR SHOWING POSTING BUTTON IN CENTRA REGION | Sethupathy A | Bugs | 2025-01-27 |  |  | 2025-01-27 17:01 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401208_071fc9b2 | NGERP HQOW CENTRA | THERE IS A MISMATCH BETWEEN THE COLUMNS AND DATA IN THE PDF AND XLSX FORMAT. | Sethupathy A | Bugs | 2025-01-27 |  |  | 2025-01-27 16:59 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401207_796a65a3 | NGERP HQOW CENTRA | PURCHASE ORDER NOT LOADING IN VENDOR RMA SCREEN | Sethupathy A | Bugs | 2025-01-27 |  |  | 2025-01-27 16:58 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Reopened |  | 0
__export__.project_task_401206_efb052b5 | NGERP HQOW CENTRA | PRODUCT COST | Sethupathy A | Bugs | 2025-01-27 |  |  | 2025-01-27 16:56 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401204_9e5e1f35 | NGERP HQOW CENTRA | EXTRA TAB RMA TAX IN VENDOR RMA SCREEN. IT SHOULD ONLY SHOW IN HQ, BUT IT IS SHOWING IN REGION | Sridhar S | Bugs | 2025-01-27 |  |  | 2025-01-27 16:53 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401203_ab43137e | NGERP HQOW CENTRA | PARTNER ADDRESS IS NOT SHOWING IN PAYMENT - AP PAYMENT PRINT FORMAT | Kishore R | Bugs | 2025-01-27 |  |  | 2025-01-27 16:52 | Krishnakumar R | 0 | 8 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401202_96e67c4b | NGERP HQOW CENTRA | WHILE ZOOMING IN BUSINESS PARTNER IT REDIRECTS TO MANAGE PARTNER SCREEN. BUT IN ROW IT REDIRECTS TO BUSINESS PARTNER | Sridhar S | Bugs | 2025-01-27 |  |  | 2025-01-27 16:51 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401201_2e165e1d | NGERP HQOW CENTRA | MATERIAL RECEIPT AUTHORIZATION SCREEN IN HQ MISSING POSTED BUTTON | Sathish K | Bugs | 2025-01-27 |  |  | 2025-01-27 16:51 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401200_6f5ff932 | NGERP HQOW CENTRA | MATERIAL RECEIPT MISSING PRINT FORMAT IN CENTRA HQ UM_GRN_HEADER_V MATERIAL RECEIPT AUTHORIZATION MISSING PRINT FORMAT IN CENTRA HQ UM_GRN_HEADER_V | Sathish K | Bugs | 2025-01-27 |  |  | 2025-01-27 16:50 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401199_86f1a548 | NGERP HQOW CENTRA | CREATE RETURN LINES IS MISSING IN MATERIAL RECEIPT AUTHORIZATION SCREEN | Sathish K | Bugs | 2025-01-27 |  |  | 2025-01-27 16:48 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401198_29d6302d | NGERP HQOW CENTRA | RECEIPT NOTE-MR_VERSION1 PRINT FORMAT HAS EXTRA DATA | Sridhar S | Bugs | 2025-01-27 |  |  | 2025-01-27 16:47 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401195_a6dfabd6 | NGERP HQOW CENTRA | EXPENSE TYPE FILED TAB ISSUE | Kishore R | Bugs | 2025-01-17 |  |  | 2025-01-27 16:45 | Krishnakumar R | 0 | 4 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401194_edc18bc9 | NGERP HQOW CENTRA | IMPORT DISCOUNT SCHEMA | Sridhar S | Bugs | 2025-01-17 |  |  | 2025-01-27 16:44 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401192_965ee427 | NGERP HQOW CENTRA | VENDOR LIST REPORT | Kishore R | Bugs | 2025-01-17 |  |  | 2025-01-27 16:43 | Krishnakumar R | 0 | 8 |  | INTERNAL-AFTER-UAT-RELEASE | Resolved |  | 0 | Surya
__export__.project_task_401191_a40ed508 | NGERP HQOW CENTRA | PAYMENT – AP | Sridhar S | Bugs | 2025-01-17 |  |  | 2025-01-27 16:42 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401185_6385ad3b | NGERP HQOW CENTRA | INVOICE (VENDOR) | Sridhar S | Bugs | 2025-01-17 |  |  | 2025-01-27 15:59 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401184_8763ea46 | NGERP HQOW CENTRA | WHILE OPENING DEPARTMENT 500 SQL EXCEPTION SHOWING | Sridhar S | Bugs | 2025-01-17 |  |  | 2025-01-27 15:56 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401179_846aaa42 | NGERP HQOW CENTRA | VENDOR INFO LINE ISSUE | Mohideen Imthiaz S | Bugs | 2025-01-17 |  |  | 2025-01-27 15:00 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401178_cec3451b | NGERP HQOW CENTRA | MANAGE PARTNER, BANK ACCOUNT TAB, BANK FILED FILED DROP DOWN SHOWS EMPTY VALUE | Sridhar S | Bugs | 2025-01-17 |  |  | 2025-01-27 14:52 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401080_edee1be9 | NGERP HQOW CENTRA | INVENTORY VALLUATION REPORT MISSING IN ROW. | Kishore R | Bugs | 2025-01-17 |  |  | 2025-01-18 14:30 | Krishnakumar R | 0 | 4 |  | INTERNAL-AFTER-UAT-RELEASE | Resolved |  | 0 | Surya
__export__.project_task_401079_573366e2 | NGERP HQOW CENTRA | MASTER INVENTORY PACKAGE REPORT SHOW DUPLICATE IN HQOW AND ROW. | Mohideen Imthiaz S | Bugs | 2025-01-17 |  |  | 2025-01-18 14:29 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Resolved |  | 0 | Surya
__export__.project_task_401078_11cd6257 | NGERP HQOW CENTRA | UNRECONCILED PAYMENTS | Mohideen Imthiaz S | Bugs | 2025-01-17 |  |  | 2025-01-18 14:28 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Resolved |  | 0 | Surya
__export__.project_task_401077_136f4040 | NGERP HQOW CENTRA | UNALLOCATED INVOICES MISSING IN ROW. | Mohideen Imthiaz S | Bugs | 2025-01-17 |  |  | 2025-01-18 14:27 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Resolved |  | 0 | Surya
__export__.project_task_401076_c0dc2f50 | NGERP HQOW CENTRA | UNALLOCATED AR&AP PAYMENT REPORT | Sathish K | Bugs | 2025-01-17 |  |  | 2025-01-18 14:25 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Resolved |  | 0 | Santhosh
__export__.project_task_401075_b4ccd8c5 | NGERP HQOW CENTRA | RMA CATEGORY HQOW DOC TYPE ISSUE IN CENTRA BUGS | Mohideen Imthiaz S | Bugs | 2025-01-17 |  |  | 2025-01-18 12:56 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401074_841c8a2c | NGERP HQOW CENTRA | PRODUCT BRAND ISSUE IN ROW CENTRA (BRAND) ADDED BUGS | Mohideen Imthiaz S | Bugs | 2025-01-17 |  |  | 2025-01-18 12:55 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401073_75d5996d | NGERP HQOW CENTRA | NTA PRODUCT CATEGORY ACCOUNTING SCHEMA LINE MISSING IN CENTRA BUGS | Thinesh Raajan S | Bugs | 2025-01-17 |  |  | 2025-01-18 12:54 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401072_f927993f | NGERP HQOW CENTRA | MANAGE PARTNER UM_Delivery RegDate UN NESSCARY SCREEN IN CENTRA ROW BUGS | Mohideen Imthiaz S | Bugs | 2025-01-17 |  |  | 2025-01-18 12:54 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Resolved |  | 0 | Santhosh
__export__.project_task_401071_5ce52864 | NGERP HQOW CENTRA | MANAGE PARTNER SCREEN CENTRA UPICODE COLUMN BUGS | Mohideen Imthiaz S | Bugs | 2025-01-17 |  |  | 2025-01-18 12:53 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401070_e00383e6 | NGERP HQOW CENTRA | CUSTOMER NO SALES REPORT – ROW | Sethupathy A | Bugs | 2025-01-17 |  |  | 2025-01-18 12:52 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Resolved |  | 0 | Santhosh
__export__.project_task_401069_868c790d | NGERP HQOW CENTRA | DEPARTMENT FIELD IS NOT SHOWING IN AWS HQ | Sethupathy A | Bugs | 2025-01-17 |  |  | 2025-01-18 12:50 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401068_61e275cf | NGERP HQOW CENTRA | BRANCH SHOULD NOT BE (*) AS DEFAULT - IMPORT CAMPAIGN MAPPING | Mohideen Imthiaz S | Bugs | 2025-01-17 |  |  | 2025-01-18 12:47 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401067_4b20126e | NGERP HQOW CENTRA | PROCESS BUTTON NOT MAPPED TO USER | Sethupathy A | Bugs | 2025-01-17 |  |  | 2025-01-18 12:46 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Reopened |  | 0
__export__.project_task_401066_a3e54665 | NGERP HQOW CENTRA | INDIVIDUAL CREDIT REPORT SHOW DUPLICATE RECORDS. | Sridhar S | Bugs | 2025-01-17 |  |  | 2025-01-18 12:45 | Krishnakumar R | 0 | 3 |  | INTERNAL-AFTER-UAT-RELEASE | Resolved |  | 0 | Santhosh
__export__.project_task_401065_ed56e5bb | NGERP HQOW CENTRA | DATE PARAMETER NOT WORKING IN REVERSED VOID INVOICE LIST REPORT | Sridhar S | Bugs | 2025-01-17 |  |  | 2025-01-18 12:44 | Krishnakumar R | 0 | 2 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401064_0f027608 | NGERP HQOW CENTRA | IMPORT REPORT LINE SET IS N0T SHOWING IN ROW CENTRA AWS | Mohideen Imthiaz S | Bugs | 2025-01-17 |  |  | 2025-01-18 12:42 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401063_38eaa694 | NGERP HQOW CENTRA | GROUP OF ATTRIBUTES IN ROW CENTRA BUGS | Sethupathy A | Bugs | 2025-01-17 |  |  | 2025-01-18 12:41 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401062_d735fe05 | NGERP HQOW CENTRA | DOCUMENT SQUENCE ROW (DOCUMENT TYPE) MISSING IN MAIN SCREEN.BUGS | Mohideen Imthiaz S | Bugs | 2025-01-17 |  |  | 2025-01-18 12:40 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401061_10bfa567 | NGERP HQOW CENTRA | DEPARTMENT LINE DIVISION MISSING.BUGS - Line column missing | Mohideen Imthiaz S | Bugs | 2025-01-17 |  |  | 2025-01-18 12:36 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Resolved |  | 0 | Santhosh
__export__.project_task_401060_b84ee4e1 | NGERP HQOW CENTRA | CURRENCY CENTRA CUSTOM 2 SCREEN NOT SHOW.BUGS - Line column missing | Mohideen Imthiaz S | Bugs | 2025-01-17 |  |  | 2025-01-18 12:36 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401059_e8da6b97 | NGERP HQOW CENTRA | ATTRIBUTE INSTANCES NOT CREATE LINE IN CENTRA ROW BUGS BUGS | Mohideen Imthiaz S | Bugs | 2025-01-17 |  |  | 2025-01-18 12:35 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Resolved |  | 0 | Santhosh
__export__.project_task_401058_28752b49 | NGERP HQOW CENTRA | ABORT WORKFLOW PROCESS NOT SHOWING SCREEN IN ROW BUGS BUGS | Mohideen Imthiaz S | Bugs | 2025-01-17 |  |  | 2025-01-18 12:12 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401057_1ddd1b4f | NGERP HQOW CENTRA | WHILE COMPLETING THE RBT THROW THE ERROR TALLY SHEET ASI IS NOT AVAILABLE | Sridhar S | Bugs | 2025-01-17 |  |  | 2025-01-18 12:11 | Krishnakumar R | 0 | 4 |  | INTERNAL-AFTER-UAT-RELEASE | Resolved |  | 0 | Santhosh
__export__.project_task_401056_bb467fa8 | NGERP HQOW CENTRA | AR INVOICE REVERSAL (E_INVOICE) NOT WORKING E_INVOICES STATUS COLUMN VALUE SHOW READY TO REVERSE | Sridhar S | Bugs | 2025-01-17 |  |  | 2025-01-18 12:10 | Krishnakumar R | 0 | 5 |  | INTERNAL-AFTER-UAT-RELEASE | Resolved |  | 0 | Praveen
__export__.project_task_401055_5ad9c63b | NGERP HQOW CENTRA | MARKETING CAMPAIGN (TRADE) SHOULD NOT LOAD IN NTA AP INVOICE LINE | Kishore R | Bugs | 2025-01-17 |  |  | 2025-01-18 12:09 | Krishnakumar R | 0 | 8 |  | INTERNAL-AFTER-UAT-RELEASE | Resolved |  | 0 | Praveen
__export__.project_task_401054_5894fb0c | NGERP HQOW CENTRA | MASTER CUSTOMER LIST_ALL | Mohideen Imthiaz S | Bugs | 2025-01-17 |  |  | 2025-01-18 11:57 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401053_6c034b61 | NGERP HQOW CENTRA | MASTER CUSTOMER CHANGE LIST_DIRECT REPORT ISSUE | Kishore R | Bugs | 2025-01-17 |  |  | 2025-01-18 11:56 | Krishnakumar R | 0 | 8 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401052_d3f3f3d0 | NGERP HQOW CENTRA | #401052 - AFTER COMPLETING GOODS RECEIPT DATE ORDERED FIELD SHOULD BE EDITABLE BUT IT’S NOT IN CENTRA (copy) | Kishore R | Bugs | 2025-01-17 |  |  | 2025-01-18 11:55 | Krishnakumar R | 0 | 8 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401050_419a0610 | NGERP HQOW CENTRA | MARKETING CAMPAIGN (TRADE) SHOULD NOT LOAD IN NTA PURCHASE ORDER LINE | Sridhar S | Bugs | 2025-01-17 |  |  | 2025-01-18 11:51 | Krishnakumar R | 0 | 4 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401049_53949203 | NGERP HQOW CENTRA | PRINT FORMATE ORDER_HEADER ** 1000002 **_VERSION1 IN PURCHASE ORDER PAYMENT TERM IS MISSING “ND” AND TEXT IS OVERLAPPED | Sethupathy A | Bugs | 2025-01-17 |  |  | 2025-01-18 10:45 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401048_d99d76c8 | NGERP HQOW CENTRA | C_ORDER_HEADER_V2 PRINT FORMATE IS SHOWING IN 8182 BUT NOT SHOWING IN CENTRA HQ | Sethupathy A | Bugs | 2025-01-17 |  |  | 2025-01-18 10:45 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401047_81ec86ca | NGERP HQOW CENTRA | TELE NO COLUMN IN PURCHASE ORDER PRINT FORMATE PO_DENEAST_VERSION_2 IS NOT PRESENT IN ROW BUT PRESENT IN CENTRA. | Sethupathy A | Bugs | 2025-01-17 |  |  | 2025-01-18 10:44 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401046_8592d039 | NGERP HQOW CENTRA | CONFIRM DMS EXPORT FORM NOT SHOWING IN CENTRA ROW. | Sethupathy A | Bugs | 2025-01-17 |  |  | 2025-01-18 10:42 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Resolved |  | 0 | Praveen
__export__.project_task_401045_9c7ea407 | NGERP HQOW CENTRA | POSTING BUTTON DISPLAYS IN ROW - PHYSICAL INVENTORY | Sridhar S | Bugs | 2025-01-17 |  |  | 2025-01-18 10:41 | Krishnakumar R | 0 | 2 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401044_5c7719c9 | NGERP HQOW CENTRA | PROCESS BUTTON NOT MAPPED TO USER | Yogan P | Bugs | 2025-01-17 |  |  | 2025-01-18 10:40 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401043_9c038ecc | NGERP HQOW CENTRA | COULD NOT IMPORT THE ORDER (SHOWING ERROR IN IMPORT PROMOTION ORDER SCREEN & 7 ORG DATA) | Sethupathy A | Bugs | 2025-01-17 |  |  | 2025-01-18 10:39 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Resolved |  | 0 | Praveen
__export__.project_task_401042_acd70fbd | NGERP HQOW CENTRA | Could not able to Import Business partner in ROW SQL Error is showing | Sethupathy A | Bugs | 2025-01-17 |  |  | 2025-01-18 10:37 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401041_b789edec | NGERP HQOW CENTRA | SELL_OUT-QUANTITY REPORT Perfomance issue | Kishore R | Bugs | 2025-01-17 |  |  | 2025-01-18 10:33 | Krishnakumar R | 0 | 8 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401040_bee5beb9 | NGERP HQOW CENTRA | Delivery Order Confirmation Report | Yogan P | Bugs | 2025-01-17 |  |  | 2025-01-17 17:02 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401039_8bb5d4a8 | NGERP HQOW CENTRA | VIEW ALLOCATION REPORT AP, VIEW ALLOCATION REPORT AR | Sridhar S | Bugs | 2025-01-17 |  |  | 2025-01-17 17:01 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401038_c5cdcc8c | NGERP HQOW CENTRA | RETURN TO POLICY ISSUE 8181 ROW CHECK CENTRA ROW RETURN TO POLICY EDITABLE BUGS | Yogan P | Bugs | 2025-01-17 |  |  | 2025-01-17 17:00 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401037_69423fcc | NGERP HQOW CENTRA | OPEN MOVE CONFIRMATION | Sathish K | Bugs | 2025-01-17 |  |  | 2025-01-17 16:59 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Resolved |  | 0 | Praveen
__export__.project_task_401036_d3d8cf0c | NGERP HQOW CENTRA | TOTAL SALES MTS BY SALESMAN | Sathish K | Bugs | 2025-01-17 |  |  | 2025-01-17 16:58 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Resolved |  | 0 | Praveen
__export__.project_task_401035_514e0e98 | NGERP HQOW CENTRA | SUMMARY OUTSTANDING COMMERCIAL REPORT MISSING IN ROW | Sathish K | Bugs | 2025-01-17 |  |  | 2025-01-17 16:57 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Resolved |  | 0 | Praveen
__export__.project_task_401034_bc8b65fc | NGERP HQOW CENTRA | PAYMENT TRANSACTION LOG | Yogan P | Bugs | 2025-01-17 |  |  | 2025-01-17 16:57 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Resolved |  | 0 | Vinesh
__export__.project_task_401033_6d0fe3a5 | NGERP HQOW CENTRA | OUT STANDING COMMERCIAL DISCOUNT REPORT-ROW | Sathish K | Bugs | 2025-01-17 |  |  | 2025-01-17 16:56 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Resolved |  | 0 | Vinesh
__export__.project_task_401032_01e14aae | NGERP HQOW CENTRA | SALES ORDER SUMMARY | Sathish K | Bugs | 2025-01-17 |  |  | 2025-01-17 16:55 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Resolved |  | 0 | Vinesh
__export__.project_task_401031_d2473c13 | NGERP HQOW CENTRA | EARLY PAYMENT REPORT MISSING IN ROW | Yogan P | Bugs | 2025-01-17 |  |  | 2025-01-17 16:55 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Resolved |  | 0 | Vinesh
__export__.project_task_401030_67d7d48a | NGERP HQOW CENTRA | SALES BY INVOICE DATE | Sathish K | Bugs | 2025-01-17 |  |  | 2025-01-17 16:54 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Resolved |  | 0 | Vinesh
__export__.project_task_401029_29989683 | NGERP HQOW CENTRA | PO MATCHING DETAILS | Yogan P | Bugs | 2025-01-17 |  |  | 2025-01-17 16:48 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401028_02ce8743 | NGERP HQOW CENTRA | AGING REPORT | Yogan P | Bugs | 2025-01-17 |  |  | 2025-01-17 16:47 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Reopened |  | 0
__export__.project_task_401027_ad14cefa | NGERP HQOW CENTRA | Reports acl issue | Yogan P | Bugs | 2025-01-17 |  |  | 2025-01-17 16:45 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401026_ff0b5ca5 | NGERP HQOW CENTRA | IMPORT RS-PURCHASE IS NOTSHOWING IN ROW CENTRA AWS | Sathish K | Bugs | 2025-01-17 |  |  | 2025-01-17 15:35 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401023_ed59324e | NGERP HQOW CENTRA | IMPORT FEE GROUP MISSING IN HQOW CENTRA | Kishore R | Bugs | 2025-01-17 |  |  | 2025-01-17 11:47 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401022_398a9777 | NGERP HQOW CENTRA | GL CATEGORY SCREEN MISSING | Yogan P | Bugs | 2025-01-17 |  |  | 2025-01-17 11:46 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Rejected |  | 0
__export__.project_task_401021_b11c637b | NGERP HQOW CENTRA | BUSINESS PAARTNER CUSTOMER LINEISSUE IN (FREIGHT) Column MISSING in Customer Tab CENTRA REGION BUGS | Sridhar S | Bugs | 2025-01-17 |  |  | 2025-01-17 11:23 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Resolved |  | 0 | Vinesh
__export__.project_task_401020_f3f29e65 | NGERP HQOW CENTRA | IMPORTED RS – TRANSFER SHOWING BRANCH IN * IT WILL NOT MOVE TO MAIN SCREENS | Sathish K | Bugs | 2025-01-17 |  |  | 2025-01-17 11:23 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Resolved |  | 0 | Vinesh
__export__.project_task_401019_a9891866 | NGERP HQOW CENTRA | IMPORTED NTA PURCHASE ORDER DATE FIELD SHOWS READ ONLY | Yogan P | Bugs | 2025-01-17 |  |  | 2025-01-17 11:22 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Resolved |  | 0 | Gobi
__export__.project_task_401241_8eec0aed | NGERP HQOW CENTRA | NET OFF RECIEPT AND NET OFF ALLOCATION NEGIATIVE AMOUNTS ALLOCATION NOT PROPERLY WORKED | Thinesh Raajan S | Bugs | 2024-08-23 |  |  | 2025-01-29 18:44 | Manirathnam T | 0 | 0 |  | Form Access | Closed |  | 0
BUG
INTERNAL-AFTER-UAT-RELEASE
__export__.project_task_401243_7aff480d | NGERP HQOW CENTRA | General Ledger line takking more time to open(Performance Issue) | SaravananV | Bugs | 2025-01-29 |  |  | 2025-01-30 11:15 | Hariharan P | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | New |  | 0
__export__.project_task_400899_0bb89d52 | NGERP HQOW CENTRA | NTA PO and GR tranasaction details should not show in ROW(Report Name - Order Transaction details). | Mohideen Imthiaz S | Bugs | 2025-01-06 |  |  | 2025-01-06 12:22 | Manjula D | 0 | 0 |  | REPORTS 290 | Resolved |  | 0 | Gobi
INTERNAL-AFTER-UAT-RELEASE
__export__.project_task_400878_6f7caccb | NGERP HQOW CENTRA | Order Transaction Report - This Report show all the region transaction's . but it should show login region transaction's details only | Mohideen Imthiaz S | Bugs | 2024-07-11 |  |  | 2025-01-03 17:29 | Manjula D | 0 | 0 |  | REPORTS 290 | Resolved |  | 0 | Gobi
INTERNAL-AFTER-UAT-RELEASE
__export__.project_task_400880_b57d4fdd | NGERP HQOW CENTRA | Physical inventory display in ROW (screen : Physical Inventory) | Mohideen Imthiaz S | Bugs | 2024-08-13 |  |  | 2025-01-03 17:35 | Manjula D | 0 | 0 |  | Transaction | Resolved |  | 0 | Gobi
INTERNAL-AFTER-UAT-RELEASE
__export__.project_task_400542_c0a17156 | NGERP HQOW CENTRA | "Attribute" tab missing in "Internal Transfer" screen for User "NGUYELL30" | Sridhar S | Bugs | 2024-12-12 |  |  | 2024-12-13 18:15 | Manjula D | 0 | 0 |  | Transaction | Resolved |  | 0 | Gobi
BUG
INTERNAL-AFTER-UAT-RELEASE
__export__.project_task_400541_18dafde2 | NGERP HQOW CENTRA | Import Treasury Management Temp screen issues listed. | Yogan P | Bugs | 2024-12-13 |  |  | 2024-12-13 17:43 | Hariharan P | 0 | 1 |  | INTERNAL-AFTER-UAT-RELEASE | Resolved |  | 0 | Gobi
__export__.project_task_400521_95ee53da | NGERP HQOW CENTRA | Login warehouse only should show in Product --->warehouse field | Sridhar S | Bugs | 2024-12-12 |  |  | 2024-12-12 14:49 | Manjula D | 0 | 4 |  | Transaction | Resolved |  | 0 | Gobi
BUG
INTERNAL-AFTER-UAT-RELEASE
__export__.project_task_400538_92c41a08 | NGERP HQOW CENTRA | Child SKU are not showing in Manage DO Print(RCA fix) | Sridhar S | Bugs | 2024-12-13 |  |  | 2024-12-13 16:46 | Manjula D | 0 | 3 |  | Transaction | Resolved |  | 0 | -
BUG
INTERNAL-AFTER-UAT-RELEASE
__export__.project_task_400559_4fa5d550 | NGERP HQOW CENTRA | #400559 - NTA AP Invoice Batch Approval: #398707 - NTA AP Invoice Batch: 43103--> Tax issue of AP invoice relates to InvoiceType = Direct Invoice issue in centra applications (CR) | Mohideen Imthiaz S | Bugs | 2024-12-08 |  |  | 2024-12-16 15:27 | Manirathnam T | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_400558_85916fc2 | NGERP HQOW CENTRA | #400558 - #398707 - NTA AP Invoice Batch: 43103--> Tax issue of AP invoice relates to InvoiceType = Direct Invoice issue in centra applications | Mohideen Imthiaz S | Bugs | 2024-12-01 |  |  | 2024-12-16 15:25 | Manirathnam T | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_400474_9ef2f44e | NGERP HQOW CENTRA | Import RS - Purchase and Import RS - Den east temp screen data clear when import RS - Transfer. | Mohideen Imthiaz S | Bugs | 2024-12-07 |  |  | 2024-12-07 12:50 | Manjula D | 0 | 0 |  | BUG | Resolved |  | 0 | -
INTERNAL-AFTER-UAT-RELEASE
__export__.project_task_400543_0c7d326e | NGERP HQOW CENTRA | Import Treasury Management with Different region in same file should not allow to import. | Yogan P | Bugs | 2024-12-13 |  |  | 2024-12-13 18:19 | Hariharan P | 0 | 2 |  | INTERNAL-AFTER-UAT-RELEASE | Resolved |  | 0 | -
__export__.project_task_400471_fc9b06af | NGERP HQOW CENTRA | System allow to create Purchase order in HQ(*). PO created via Recommented shipment(MLD). | Mohideen Imthiaz S | Bugs | 2024-12-07 |  |  | 2024-12-07 12:06 | Manjula D | 0 | 0 |  | BUG | Resolved |  | 0 | -
INTERNAL-AFTER-UAT-RELEASE
__export__.project_task_401240_9534ebf2 | NGERP HQOW CENTRA | NTA RECIEPT ALLOCATION SCREEN WRITE OFF ALLOCATION NOT PROPERLY WORKED | Thinesh Raajan S | Bugs | 2024-08-08 |  |  | 2025-01-29 18:40 | Manirathnam T | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401223_884b2836 | NGERP HQOW CENTRA | TRANSACTION DATA NOT SHOWING IN GOODS RECEIVE ADVICE PRINT IN INVOICE(VENDOR) SCREEN FOR CUSTOM CLEARANCE INVOICE. | Kishore R | Bugs | 2025-01-27 |  |  | 2025-01-28 10:36 | Krishnakumar R | 0 | 8 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401209_82b22bdb | NGERP HQOW CENTRA | DUPLICATE TAX ISSUE “1NPO2311-10136 ”WHEN IMPORT THE MULITIPLE NTA PO RECORDS IN CENTRA | Thinesh Raajan S | Bugs | 2025-01-27 |  |  | 2025-01-27 17:00 | Krishnakumar R | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | New |  | 0
__export__.project_task_401205_9bc39e8c | NGERP HQOW CENTRA | IMPORT ROLE DOESNT HAVE ANY BRANCH FILTER TO CHANGE READ/WRITE,ACTIVE FOR SPECIFIC BRANCH (ONLY CHANGES *) | Kishore R | Bugs | 2025-01-27 |  |  | 2025-01-27 16:55 | Krishnakumar R | 0 | 8 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401197_56128474 | NGERP HQOW CENTRA | IMPORT FEE GROUP CENTRA ROW R1 CREATE BUTTON ISSUE | Kishore R | Bugs | 2025-01-27 |  |  | 2025-01-27 16:46 | Krishnakumar R | 0 | 8 |  | INTERNAL-AFTER-UAT-RELEASE | Closed |  | 0
__export__.project_task_401232_e9adfcd6 | NGERP HQOW CENTRA | Import NTA Goods Receipt Issues listed. | Sridhar S | Bugs | 2025-01-28 |  |  | 2025-01-28 18:54 | Hariharan P | 0 | 0 |  | INTERNAL-AFTER-UAT-RELEASE | New |  | 0